## Basic (hidden)
#REF!
| #REF! | [10 empty] | Estimate as per Primemetal BQ
#REF!
| Estimate as per BQ of Paul Wurth |  |  |  |  | Euro= |  | #REF! |  |  |  | ASSIGN. NO.- 01/DE/4904 |  |  |  |  | Euro= |  | #REF!
[10 empty] | Observations: | [10 empty] | Observations:
Sl. No, | Description | Unit | Qty. | Unit Rate (LC)- Rs. | Amt. (Rs. L) LC | Rate (FC) | Amt. (Rs. L) FC | Basis / Remarks | Quote |  | Sl. No, | Description | Unit | Qty. | Unit Rate (LC)- Rs. | Amt. (Rs. L) LC | Rate (FC) | Amt. (Rs. L) FC | Basis / Remarks | Quote
A | Equpment | [9 empty] | A | Equpment | [7 empty] | 9788
| Technological equipment | [7 empty] | 6000 | As per BQ of M/S PW |  | Technological equipment | [7 empty] | 8000 | As per BQ of M/S PW
1(a) | Installation of 4th Stove at B.F 8, BSP including mechanical, refractory, utility & services, civil & structural and associted electrics & Instrumentation & Automation. | Lot | 1 | 268712136.0172 | 2687.1214 | 0 | 0 | BQ Paul Wurth (PW) dtd 30.12.2021 validity of BQ upto March 2022 dated 25.01.2022 (D&E @7.5% and Erec @12% deducted), Discounted by 25% | 3300 |  | 1(a) | Installation of 4th Stove at B.F 8, BSP including mechanical, refractory, utility & services, civil & structural and associted electrics & Instrumentation & Automation. | Lot | 1 | 332225913.6213 | 3322.2591 | 0 | 0 | BQ Paul Wurth (PW) dtd 30.12.2021 validity of BQ upto March 2022 dated 25.01.2022 (D&E @7.5% and Erec @12% deducted) | 4000
1(b) | Installation of 4th Stove at B.F 8, BSP including mechanical, refractory, utility & services and associted electrics & Instrumentation & Automation. | Lot | 1 | 637358139.5349 | 6373.5814 | 0 | 0 | BQ PRIMETALS (PM) Technologies dtd 21.01.2022 (D&E @7.5% deducted) | 6851.6 | As per BQ of M/S PM | 1(b) | Installation of 4th Stove at B.F 8, BSP including mechanical, refractory, utility & services and associted electrics & Instrumentation & Automation. | Lot | 1 | 637358139.5349 | 6373.5814 | 0 | 0 | BQ PRIMETALS (PM) Technologies dtd 21.01.2022 (D&E @7.5% deducted) | 6851.6 | As per BQ of M/S PM
1 (c ) | Installation of 4th Stove at B.F 8, BSP including mechanical, refractory, utility & services, civil & structural and associted electrics & Instrumentation & Automation. | Lot | 1 | 0 |  | 12981727.5748 | #REF! | BQ M/s DC dtd 16.12.2021 (presumption-D&E @7.5% and Erec @12% deducted) | #REF! | As per BQ of M/S DC | 1 (c ) | Installation of 4th Stove at B.F 8, BSP including mechanical, refractory, utility & services, civil & structural and associted electrics & Instrumentation & Automation. | Lot | 1 | 0 |  | 12981727.5748 | #REF! | BQ M/s DC dtd 16.12.2021 (presumption-D&E @7.5% and Erec @12% deducted) | #REF! | As per BQ of M/S DC
| Equipments Which are not Included in respective BQ (1(b), 1(b), 1(c )) | [6 empty] | Equipment has been taken by all the 3 parties. |  |  |  | Equipments Which are not Included in respective BQ (1(b), 1(b), 1(c )) | [6 empty] | Equipment has been taken by all the 3 parties.
| Sub-total (Equipment) |  |  |  | 2687.1214 | [6 empty] | Sub-total (Equipment) |  |  |  | 6373.5814
B | Spares | [10 empty] | Spares
| 2 Year O&M Spares |  |  |  | 80.6136 |  |  | Spares (@ 3% of Indigenous Ept & @5% of Imported Eqpt. |  | Common data for 1(a), 1(b), 1(c) |  | 2 Year O&M Spares |  |  |  | 191.2074 |  |  | Spares (@ 3% of Indigenous Ept & @5% of Imported Eqpt. |  | Common data for 1(a), 1(b), 1(c)
C | REFRACTORY | [10 empty] | REFRACTORY
| Rafractory which are Included in respective BQ (1(a), 1(b), 1(c )) | LS | 1 | 137157487.2748 | 1371.5749 |  |  | 30% of BQ cost - M/s PW (1 (a)),(D&E @7.5% and Erec @12% deducted) | 1800 | 30% of the BQ cost is only for M/s Paul Wurth & M/s Primetals. No data for M/s DC |  | Rafractory which are Included in respective BQ (1(a), 1(b), 1(c )) | LS | 1 | 273153488.3721 | 2731.5349 |  |  | 30% of BQ cost - M/s PM (1 (b)),(D&E @7.5% deducted) | 2936.4 | 30% of the BQ cost is only for M/s Paul Wurth & M/s Primetals. No data for M/s DC
| Refractory which are not Included in respective BQ (1(a), 1(b), 1(c )) | [6 empty] | No exclusion for Refractory by all the 3 parties |  | Refractory cost in included in BQ cost by all parties. |  | Refractory which are not Included in respective BQ (1(a), 1(b), 1(c )) | [6 empty] | No exclusion for Refractory by all the 3 parties |  | Refractory cost in included in BQ cost by all parties.
| Sub-total (Refractory) |  |  |  | 1371.5749 | [6 empty] | Sub-total (Refractory) |  |  |  | 2731.5349
D | STRUCTURES | [10 empty] | STRUCTURES
| Technological Structure which are Included in respective BQ (1(a), 1(c )) | LS | 1 | 21335609.1316 | 213.3561 |  |  | 5% of BQ cost - M/s PW (1 (a)), (D&E @7.5% and Erec @20% deducted) | 300 | This is only for M/s Paul Wurth 1(a). No data for M/s DC 1(c) |  | Technological Structure which are Included in respective BQ (1(a), 1(c )) | LS | 0 | 31007751.938 | 0 |  |  | 5% of BQ cost - M/s PW (1 (a)), (D&E @7.5% and Erec @20% deducted) | 400 | This is only for M/s Paul Wurth 1(a). No data for M/s DC 1(c)
| Technological Structure which are not Included in BQ 1(b) | t | 0 | 100000 | 0 |  |  | Structural jobs excluded in the offer of M/s PM 1(b). Estimated quantity based on 4th stove of B.F 5, RSP |  | This is only for M/s Primetals as they have taken exclusions 1(b) |  | Technological Structure which are not Included in BQ 1(b) | t | 700 | 100000 | 700 |  |  | Structural jobs excluded in the offer of M/s PM 1(b). Estimated quantity based on 4th stove of B.F 5, RSP |  | This is only for M/s Primetals as they have taken exclusions 1(b)
| Sub-total (Tech. Str.) |  |  |  | 213.3561 | [6 empty] | Sub-total (Tech. Str.) |  |  |  | 700
| Building Structure which are Included in respective BQ (1(a), 1(c )) | LS | 1 | 21335609.1316 | 213.3561 |  |  | 5% of BQ cost - M/s PW (1 (a)), (D&E @7.5% and Erec @20% deducted) | 300 | This is only for M/s Paul Wurth 1(a). No data for M/s DC 1(c) |  | Building Structure which are Included in respective BQ (1(a), 1(c )) | LS | 0 | 31007751.938 | 0 |  |  | 5% of BQ cost - M/s PW (1 (a)), (D&E @7.5% and Erec @20% deducted) | 400 | This is only for M/s Paul Wurth 1(a). No data for M/s DC 1(c)
| Building Structure which are not Included in BQ 1(b) | t | 0 | 85000 | 0 |  |  | Structural jobs excluded in the offer of M/s PM 1(b). Estimated quantity based on 4th stove of B.F 5, RSP. |  | This is only for M/s Primetals as they have taken exclusions 1(b) |  | Building Structure which are not Included in BQ 1(b) | t | 150 | 85000 | 127.5 |  |  | Structural jobs excluded in the offer of M/s PM 1(b). Estimated quantity based on 4th stove of B.F 5, RSP. |  | This is only for M/s Primetals as they have taken exclusions 1(b)
| Sub-total (Bldg. Str.) |  |  |  | 213.3561 | [6 empty] | Sub-total (Bldg. Str.) |  |  |  | 127.5
E | CIVIL WORKS | [10 empty] | CIVIL WORKS
| Civil Works for Equipment Foundation which are Included in respective BQ (1(a), 1(c )) | LS | 1 | 13953488.3721 | 139.5349 |  |  | 2.5% of BQ cost - M/s PW (1 (a)), (D&E @7.5% deducted) | 150 | This is only for M/s Paul Wurth 1(a). No data for M/s DC 1(c) |  | Civil Works for Equipment Foundation which are Included in respective BQ (1(a), 1(c )) | LS | 0 | 37209302.3256 | 0 |  |  | 5% of BQ cost - M/s PW (1 (a)), (D&E @7.5% deducted) | 400 | This is only for M/s Paul Wurth 1(a). No data for M/s DC 1(c)
| Civil Works for Equipment Foundation which are not Included in BQ 1(b) | [6 empty] | Civil jobs excluded in the offer of M/s PM 1(b). Estimated quantity given below. |  | This is only for M/s Primetals as they have taken exclusions 1(b) |  | Civil Works for Equipment Foundation which are not Included in BQ 1(b) | [6 empty] | Civil jobs excluded in the offer of M/s PM 1(b). Estimated quantity given below. |  | This is only for M/s Primetals as they have taken exclusions 1(b)
| Excavation | m3 | 0 | 377.3957 | 0 |  |  | 2.6+2.25x(0.9) |  |  |  | Excavation | m3 | 20 | 377.3957 | 0.075479 |  |  | 2.6+2.25x(0.9)
| PCC M-10 | m3 | 0 | 6068 | 0 |  |  | 4.1.6+1*4.3.1 |  |  |  | PCC M-10 | m3 | 1 | 6068 | 0.06068 |  |  | 4.1.6+1*4.3.1
| RCC M-25C | m3 | 0 | 9397.903 | 0 |  |  | 0.39x5.33.1+0.61x5.332+5x5.9.1 |  |  |  | RCC M-25C | m3 | 5 | 9397.903 | 0.4699 |  |  | 0.39x5.33.1+0.61x5.332+5x5.9.1
| Reinforcement | t | 0 | 77956.5217 | 0 |  |  | 5.22.6 |  |  |  | Reinforcement | t | 1 | 77956.5217 | 0.77957 |  |  | 5.22.6
| Insert | t | 0 | 80000 | 0 |  |  | 10.1 |  |  |  | Insert | t | 1 | 80000 | 0.8 |  |  | 10.1
| Brick on edge Soiling for Apron | m2 |  | 781.0435 | 0 |  |  | 11.1.2 |  |  |  | Brick on edge Soiling for Apron | m2 |  | 781.0435 | 0 |  |  | 11.1.2
| Boulder Soiling for grade floor | m3 |  | 3176.6184 | 0 |  |  | 16.11/0.225 |  |  |  | Boulder Soiling for grade floor | m3 |  | 3176.6184 | 0 |  |  | 16.11/0.225
| Brick Work | m3 |  | 7207.2609 | 0 |  |  | 6.4.2 |  |  |  | Brick Work | m3 |  | 7207.2609 | 0 |  |  | 6.4.2
| Outside Plater-20 thk | m2 |  | 332.2609 | 0 |  |  | 13.3.2 |  |  |  | Outside Plater-20 thk | m2 |  | 332.2609 | 0 |  |  | 13.3.2
| Inside Plaster-15 thk. | m2 |  | 282 | 0 |  |  | 13.2.2. |  |  |  | Inside Plaster-15 thk. | m2 |  | 282 | 0 |  |  | 13.2.2.
| Ceiling Plaster-6 thk. | m2 |  | 220.0435 | 0 |  |  | 13.16.1 |  |  |  | Ceiling Plaster-6 thk. | m2 |  | 220.0435 | 0 |  |  | 13.16.1
| Roof Teatment | m2 |  | 653.3333 | 0 |  |  | 14.91.1x(4/3) |  |  |  | Roof Teatment | m2 |  | 653.3333 | 0 |  |  | 14.91.1x(4/3)
| Doors, windows, Ventilators | m2 |  | 4157.5217 | 0 |  |  | 10.5.1 |  |  |  | Doors, windows, Ventilators | m2 |  | 4157.5217 | 0 |  |  | 10.5.1
| Exterior Emulsion | m2 |  | 145.087 | 0 |  |  | 13.46.1 |  |  |  | Exterior Emulsion | m2 |  | 145.087 | 0 |  |  | 13.46.1
| Interior Emulsion | m2 |  | 119.8696 | 0 |  |  | 13.60.1 |  |  |  | Interior Emulsion | m2 |  | 119.8696 | 0 |  |  | 13.60.1
| Floor Finish-IPS | m2 |  | 473.913 | 0 |  |  | 11.3.1 |  |  |  | Floor Finish-IPS | m2 |  | 473.913 | 0 |  |  | 11.3.1
| Sub-Total (Civil-Eqpt. Fdn.) |  |  |  | 139.5349 | [6 empty] | Sub-Total (Civil-Eqpt. Fdn.) |  |  |  | 2.1856
| Civil Works for other than Equipment Foundation which are Included in respective BQ (1(a), 1(c )) | LS | 1 | 13953488.3721 | 139.5349 |  |  | 2.5% of BQ cost - M/s PW (1 (a)), (D&E @7.5% deducted) | 150 | This is only for M/s Paul Wurth 1(a). No data for M/s DC 1(c) |  | Civil Works for other than Equipment Foundation which are Included in respective BQ (1(a), 1(c )) | LS | 0 | 37209302.3256 | 0 |  |  | 5% of BQ cost - M/s PW (1 (a)), (D&E @7.5% deducted) | 400 | This is only for M/s Paul Wurth 1(a). No data for M/s DC 1(c)
| Civil Works for other than Equipment Foundation which are not Included in BQ 1(b) | [6 empty] | Civil jobs excluded in the offer of M/s PM 1(b). Estimated quantity given below. |  | This is only for M/s Primetals as they have taken exclusions 1(b) |  | Civil Works for other than Equipment Foundation which are not Included in BQ 1(b) | [6 empty] | Civil jobs excluded in the offer of M/s PM 1(b). Estimated quantity given below. |  | This is only for M/s Primetals as they have taken exclusions 1(b)
| Excavation | m3 | 0 | 377.3957 | 0 |  |  | 2.6+2.25x(0.9) |  |  |  | Excavation | m3 | 380 | 377.3957 | 1.4341 |  |  | 2.6+2.25x(0.9)
| PCC M-10 | m3 | 0 | 6068 | 0 |  |  | 4.1.6+1*4.3.1 |  |  |  | PCC M-10 | m3 | 4 | 6068 | 0.24272 |  |  | 4.1.6+1*4.3.1
| RCC M-25C | m3 | 0 | 9397.903 | 0 |  |  | 0.39x5.33.1+0.61x5.332+5x5.9.1 |  |  |  | RCC M-25C | m3 | 45 | 9397.903 | 4.2291 |  |  | 0.39x5.33.1+0.61x5.332+5x5.9.1
| Reinforcement | t | 0 | 77956.5217 | 0 |  |  | 5.22.6 |  |  |  | Reinforcement | t | 5 | 77956.5217 | 3.8978 |  |  | 5.22.6
| Insert | t |  | 80000 | 0 |  |  | 10.1 |  |  |  | Insert | t |  | 80000 | 0 |  |  | 10.1
| Brick on edge Soiling for Apron | m2 | 0 | 781.0435 | 0 |  |  | 11.1.2 |  |  |  | Brick on edge Soiling for Apron | m2 | 35 | 781.0435 | 0.27337 |  |  | 11.1.2
| Boulder Soiling for grade floor | m3 | 0 | 3176.6184 | 0 |  |  | 16.11/0.225 |  |  |  | Boulder Soiling for grade floor | m3 | 20 | 3176.6184 | 0.63532 |  |  | 16.11/0.225
| Brick Work | m3 | 0 | 7207.2609 | 0 |  |  | 6.4.2 |  |  |  | Brick Work | m3 | 35 | 7207.2609 | 2.5225 |  |  | 6.4.2
| Outside Plater-20 thk | m2 | 0 | 332.2609 | 0 |  |  | 13.3.2 |  |  |  | Outside Plater-20 thk | m2 | 140 | 332.2609 | 0.46517 |  |  | 13.3.2
| Inside Plaster-15 thk. | m2 | 0 | 282 | 0 |  |  | 13.2.2. |  |  |  | Inside Plaster-15 thk. | m2 | 140 | 282 | 0.3948 |  |  | 13.2.2.
| Ceiling Plaster-6 thk. | m2 | 0 | 220.0435 | 0 |  |  | 13.16.1 |  |  |  | Ceiling Plaster-6 thk. | m2 | 70 | 220.0435 | 0.15403 |  |  | 13.16.1
| Roof Teatment | m2 | 0 | 653.3333 | 0 |  |  | 14.91.1x(4/3) |  |  |  | Roof Teatment | m2 | 100 | 653.3333 | 0.65333 |  |  | 14.91.1x(4/3)
| Doors, windows, Ventilators | m2 | 0 | 4157.5217 | 0 |  |  | 10.5.1 |  |  |  | Doors, windows, Ventilators | m2 | 20 | 4157.5217 | 0.8315 |  |  | 10.5.1
| Exterior Emulsion | m2 | 0 | 145.087 | 0 |  |  | 13.46.1 |  |  |  | Exterior Emulsion | m2 | 140 | 145.087 | 0.20312 |  |  | 13.46.1
| Interior Emulsion | m2 | 0 | 119.8696 | 0 |  |  | 13.60.1 |  |  |  | Interior Emulsion | m2 | 210 | 119.8696 | 0.25173 |  |  | 13.60.1
| Floor Finish-IPS | m2 | 0 | 473.913 | 0 |  |  | 11.3.1 |  |  |  | Floor Finish-IPS | m2 | 70 | 473.913 | 0.33174 |  |  | 11.3.1
[12 empty] | Grout | m3 | 6 | 73000 | 4.38
[12 empty] | Misc. Jobs | LS | 1 | 500000 | 5
| Sub-Total (Civil-Other) |  |  |  | 139.5349 | [6 empty] | Sub-Total (Civil-Other) |  |  |  | 25.9004
F | Dismantling | [10 empty] | Dismantling
1 | Civil works | [6 empty] | In general dismantling not required. |  | Common data for 1(a), 1(b) & 1(c) | 1 | Civil works | [6 empty] | In general dismantling not required. |  | Common data for 1(a), 1(b) & 1(c)
2 | Dismantling of structures(Lumsum) | t | 10 | 8000 | 0.8 | [5 empty] | 2 | Dismantling of structures(Lumsum) | t | 10 | 8000 | 0.8
3 | Hot blast main dished end + Thrust collar + tie rods | t | 9.5 | 12000 | 1.14 | [5 empty] | 3 | Hot blast main dished end + Thrust collar + tie rods | t | 9.5 | 12000 | 1.14
4 | Expansion joint | t | 2.5 | 12000 | 0.3 | [5 empty] | 4 | Expansion joint | t | 2.5 | 12000 | 0.3
| Sub-Total (Dismtl.) |  |  |  | 2.24 | [6 empty] | Sub-Total (Dismtl.) |  |  |  | 2.24
[5 empty] | 4847.3318 |  | Cap Cost= | #REF! | [7 empty] | 10154.1497
| Special Erection (Crane Cost) if any | [6 empty] | Not required as per cost committee meeting of 4th stove of B.F 5, RSP dt. 16.10.2021 |  | Common data for 1(a), 1(b) & 1(c) |  | Special Erection (Crane Cost) if any | [6 empty] | Not required as per cost committee meeting of 4th stove of B.F 5, RSP dt. 16.10.2021 |  | Common data for 1(a), 1(b) & 1(c)
| Foregn Supervision | Mandays | [5 empty] | Not required. |  | Common data for 1(a), 1(b) & 1(c) |  | Foregn Supervision | Mandays | [5 empty] | Not required. |  | Common data for 1(a), 1(b) & 1(c)
| Foreign Traling | Mandays | [5 empty] | Not required |  | Common data for 1(a), 1(b) & 1(c) |  | Foreign Traling | Mandays | [5 empty] | Not required |  | Common data for 1(a), 1(b) & 1(c)
| Expenditure towards Corporate Environmental Responsibility (CER) (Guideline) | [6 empty] | Not applicable as only 3 stoves at a time will run in cylcic mode. |  | Common data for 1(a), 1(b) & 1(c) |  | Expenditure towards Corporate Environmental Responsibility (CER) (Guideline) | [6 empty] | Not applicable as only 3 stoves at a time will run in cylcic mode. |  | Common data for 1(a), 1(b) & 1(c)
| Cost for engagement of NABET accredited Consultant for environmental clearance | [6 empty] | Not applicable as only 3 stoves at a time will run in cylcic mode. |  | Common data for 1(a), 1(b) & 1(c) |  | Cost for engagement of NABET accredited Consultant for environmental clearance | [6 empty] | Not applicable as only 3 stoves at a time will run in cylcic mode. |  | Common data for 1(a), 1(b) & 1(c)
| Note: as per guidelines given by CTE vide e-mail dated 30.01.2022, letters given to all the 3 parties for comply vide mail dt 31.01.2022. Reply from M/s Paul Wurth has only received till date. | [10 empty] | Note: as per guidelines given by CTE vide e-mail dated 30.01.2022, letters given to all the 3 parties for comply vide mail dt 31.01.2022. Reply from M/s Paul Wurth has only received till date.
| Civil works under exclusion (M/s PM 1(b)) | [10 empty] | Civil works under exclusion (M/s PM 1(b))
| 1) Grout = 6.0 Cum, | [6 empty] | 60.32 |  |  |  | 1) Grout = 6.0 Cum,
| DSR Code= item no. 1219 page -19 | [10 empty] | DSR Code= item no. 1219 page -19
| Basic cost of material = Rs. 28/ kg. | [10 empty] | Basic cost of material = Rs. 28/ kg.
| Consumption of material as per datasheet of Sika, Fosroc etc. is about 2000kg/cum | [10 empty] | Consumption of material as per datasheet of Sika, Fosroc etc. is about 2000kg/cum
| Cost of material for 1 cum = Rs. 56000 | [10 empty] | Cost of material for 1 cum = Rs. 56000
| Add 11% toward labour, machinery etc. = Rs.6160 | [10 empty] | Add 11% toward labour, machinery etc. = Rs.6160
| Water charges @ 1%= Rs.560 | [10 empty] | Water charges @ 1%= Rs.560
| Total= Rs. 62720 | [10 empty] | Total= Rs. 62720
| CPOH @ 15% = Rs. 9408 | [10 empty] | CPOH @ 15% = Rs. 9408
| Total = Rs. 72128/ Cum SAY Rs. 73000/cum. | [10 empty] | Total = Rs. 72128/ Cum SAY Rs. 73000/cum. |  |  | 73000
| (analysis is done in line with DAR of DSR and hence is inclusive of GST) | [10 empty] | (analysis is done in line with DAR of DSR and hence is inclusive of GST)
| 2) Miscl. Jobs = Rs. 5 Lakhs (LS)- Engineering estimate | [10 empty] | 2) Miscl. Jobs = Rs. 5 Lakhs (LS)- Engineering estimate
| (cleaning & clearing the site, drilling hole & fixing stub bars for RCC pedestals, any unforeseen RCC foundations, if required.) | [10 empty] | (cleaning & clearing the site, drilling hole & fixing stub bars for RCC pedestals, any unforeseen RCC foundations, if required.)
| 3) New Hydraulic room (size 10mX7mX4m(h)) | [10 empty] | 3) New Hydraulic room (size 10mX7mX4m(h))
| Item |  | Unit | Total Qty | Equip. | DSR-2018 Code | DSR Rate |  |  |  |  | Item |  | Unit | Total Qty | Equip. | DSR-2018 Code | DSR Rate
[5 empty] | Qty | [10 empty] | Qty
| Excavation | = | m3 | 400 | 20 | 2.6+2.25x(0.9) | 379.54 | 380 |  |  |  | Excavation | = | m3 | 400 | 20 | 2.6+2.25x(0.9) | 379.54 | 380
| PCC M-10 | = | m3 | 5 | 1 | 4.1.6+1*4.3.1 | 6410.11 | 4 |  |  |  | PCC M-10 | = | m3 | 5 | 1 | 4.1.6+1*4.3.1 | 6410.11 | 4
| RCC M-25C | = | m3 | 50 | 5 | 0.39x5.33.1+ | 10283.05 | 45 |  |  |  | RCC M-25C | = | m3 | 50 | 5 | 0.39x5.33.1+ | 10283.05 | 45
[6 empty] | 0.61x5.332+5x5.9.1 |  | 0 | [8 empty] | 0.61x5.332+5x5.9.1 |  | 0
| Reinforcement | = | t | 6 | 1 | 5.22.6 | 83500 | 5 |  |  |  | Reinforcement | = | t | 6 | 1 | 5.22.6 | 83500 | 5
| Insert | = | t | 1 | 1 | 10.1 | 86050 | 0 |  |  |  | Insert | = | t | 1 | 1 | 10.1 | 86050 | 0
| Brick on edge Soiling for Apron | = | m2 | 35 | - | 11.1.2 | 829.45 | #VALUE! |  |  |  | Brick on edge Soiling for Apron | = | m2 | 35 | - | 11.1.2 | 829.45 | #VALUE!
| Boulder Soiling for grade floor | = | m3 | 20 | - | 16.11/0.225 | 3653 | #VALUE! |  |  |  | Boulder Soiling for grade floor | = | m3 | 20 | - | 16.11/0.225 | 3653 | #VALUE!
| Brick Work | = | m3 | 35 | - | 6.4.2 | 7590.45 | #VALUE! |  |  |  | Brick Work | = | m3 | 35 | - | 6.4.2 | 7590.45 | #VALUE!
| Outside Plater-20 thk | = | m2 | 140 | - | 13.3.2 | 345.65 | #VALUE! |  |  |  | Outside Plater-20 thk | = | m2 | 140 | - | 13.3.2 | 345.65 | #VALUE!
| Inside Plaster-15 thk. | = | m2 | 140 | - | 13.2.2. | 292.85 | #VALUE! |  |  |  | Inside Plaster-15 thk. | = | m2 | 140 | - | 13.2.2. | 292.85 | #VALUE!
| Ceiling Plaster-6 thk. |  | m2 | 70 | - | 13.16.1 | 227.35 | #VALUE! |  |  |  | Ceiling Plaster-6 thk. |  | m2 | 70 | - | 13.16.1 | 227.35 | #VALUE!
| Roof Teatment |  | m2 | 100 | - | 14.91.1x(4/3) | 713.33 | #VALUE! |  |  |  | Roof Teatment |  | m2 | 100 | - | 14.91.1x(4/3) | 713.33 | #VALUE!
| Doors, windows, Ventilators | = | m2 | 20 | - | 10.5.1 | 4428.15 | #VALUE! |  |  |  | Doors, windows, Ventilators | = | m2 | 20 | - | 10.5.1 | 4428.15 | #VALUE!
| Exterior Emulsion | = | m2 | 140 | - | 13.46.1 | 164.7 | #VALUE! |  |  |  | Exterior Emulsion | = | m2 | 140 | - | 13.46.1 | 164.7 | #VALUE!
| Interior Emulsion | = | m2 | 210 | - | 13.60.1 | 128.65 | #VALUE! |  |  |  | Interior Emulsion | = | m2 | 210 | - | 13.60.1 | 128.65 | #VALUE!
| Floor Finish-IPS | = | m2 | 70 | - | 11.3.1 | 498.35 | #VALUE! |  |  |  | Floor Finish-IPS | = | m2 | 70 | - | 11.3.1 | 498.35 | #VALUE!
10154.1497

## GM (hidden)
Annexure -6.5.1-1
BOKARO STEEL PLANT
Installation of 4th Stove and Revamping of existing 3 nos. of Stoves in BF#2
GROSS MARGIN CALCULATIONS
A | Technical Parameters:
Sl.No | Description | Unit | Value
1 | Working volume of the Furnace | Cum | 1758
2 | Hot metal production (Base Case: 2020-21) | tpd | 2760.06
3 | Duration of Furnace operation/ year | Days | 350
4 | Hot Blast Temp.(Base Case: 2020-21) | °C | 912
5 | Hot Blast Temp.(Proposed Case) | °C | 1200
6 | High Top Pressure (Base Case: 2020-21) | Kg/cm2g | 0.86
7 | High Top Pressure (Proposed Case) | Kg/cm2g | 1
8 | Increase in Hot Metal production on account of increase in HBT | tpd | 118.9586
9 | Increase in Hot Metal production on account of increase in HTP | tpd | 42.5049
10 | Hot Metal Production (Proposed) | tpd | 2921.5235
11 | Addl. Hot Metal prodn | Tonne | 56512.2285
12 | Eqvt. Addl. Pig Iron (93% yield) | Tonne | 52556.3725
13 | Avg. Coke Rate (Base Case: 2020-21) | kg/tHM | 453
14 | Redn. in coke rate on account of increase in HBT | kg/tHM | 18.6183
15 | Redn. in coke rate on account of increase in HTP | kg/tHM | 3.171
16 | Avg. Coke Rate (Proposed Case) | kg/tHM | 431.2107
17 | Redn. in Coke Rate | kg/tHM | 21.7893
B | Benefits :
Sl.No | Description | Unit | Quantity (t) | Rate (Rs/t) | Amount (Rs. Cr)
1 | Contribution from Addl. Pig Iron (Avg NSR 2018-21 & VC-H1, 2021-22) | Tonne | 52556.3725 | 5487.3333 | 28.8394
2 | Savings in coke consumption (VC- H1, 2021-22) | Tonne | 22280.2833 | 23586.55 | 52.5515
| Sub-total (B) |  |  |  | 81.3909 |  |  | CO gas | 1NM3 | 4200 | kCal | 1GCal= | 4.18*10^6 | KJ
C | Expenditure: | [6 empty] | BF Gas | 1NM3 | 780 | kCal
1 | Addl. Steam (6 tph) | Tonne | 50400 | 1176.36 | 5.9289
2 | Addl. BF Gas (20000 Nm3/h) | Gcal | 131040 | 1080.19 | 14.1548
2 | DM water make up for stove @ 73 M3/hr | ThM3 | 0 | 1935.5 | 0
3 | Power @ 50kWh | MW | 0 | 5072.7 | 0
4 | Secondary Industrial Water Make up @ 5M3/hr | ThM3 | 0 | 786.44 | 0
5 | Nitrogen @ 25 NM3/hr | ThNM3 | 0 | 2216.26 | 0
6 | Repair & Maint. @ 2.5% of CC net of ITC |  |  |  | #REF!
| Sub-total (C) |  |  |  | #REF!
| Gross Margin (B-C) | Rs. Cr. |  |  | #REF! | 49.8162 | 133.9472
[6 empty] | 108.3937 | 71.4197
Basis for benefits considered due to HBT rise:
|  |  | Base case | Proposed | Incr/ Decr
| Production | tpd | 2760.06 | 2921.5235 | 161 |  | 2879.0186
| Coke Rate | kg/tHM | 453 | 431.2107 | -22
| HBT | Deg C | 912 | 1200 | 288
| Hot Blast Temp. Increase | incr. in BF productivity for every 100 deg rise in HBT | decr. in coke rate for every 100 deg rise in HBT | Temp. Increase | Coke Rate | Production
| 900-1000C | 2% | 2% | 88 | 7.9728 | 48.5771 | 158.9795 | 2% increase in production for every 100 oC HBT increase
| 1000-1100C | 1.5% | 1.5% | 100 | 6.795 | 41.4009 | 118.9586 | My calculation
| 1100-1200C | 1.05% | 0.85% | 100 | 3.8505 | 28.9806 | 43.0531 | 3.3% decrease in coke rate for every 100 oC HBT increase
| Average | 1.517% | 1.45% | Top Pressure Effect | 3.171 | 42.5049 | 18.6183 | My calculation
|  |  |  | Resultant Value | 431.2107 | 2921.5235
Effect of top pressure
1 | Top Pressure (Base Case) | Kg/cm2g | 0.86
2 | Top Pressure (Proposed case) | kg/cm2g | 1
3 | Increase in productivity due to top pressure change |  | 1.54% | 1.1% increase in production for every 0.1 kg/cm2 increase in top pressure
4 | Decrease in coke rate due to top pressure change | kg/tHM | 0.7% | 0.5% decrease in coke rate for every 0.1 kg/cm2 increase in top pressure
Loss of contribution during addl. s/d period of 120 days
1 | HM prodn.in Base Case | t | 966021
2 | Duration of BF shutdown envisaged | days | 180
3 | Sheduled Shutdown | days | 180
4 | Addl. shutdown period reqd | days | 0
5 | HM production loss during addl S/D | tonnes | 0
6 | Equivalent Pig Production | tpa | 0
7 | Contribuion loss from hot metal | Rs Cr. | 0
DATA REQUIRED FOR GROSS MARGIN CALCULATIONS (Assgn No. 02/DE/4906)
Base Data
| Item | Unit | 2018-19 | 2019-20 | 2020-21 | Avg. 3 years
| Hot Blast Temp. | oC | 901 | 869 | 912 | 894
| HM production, tpd | tpd | 2681 | 2827 | 2760.06 | 2756.02
| Coke Rate, kg/thm | Kg/tHM | 465.9955 | 492.5197 | 453 | 470.7264
| Top Pressure, kg/cm2 | kg/cm2 | 0.89 | 0.86 | 0.86 | 0.87
| Steam, tph | tph | 1.96 | 4 | 4 | 3.32
| BF gas consumption in stoves, Nm3/h | Nm3/h | 90000 | 90000 | 90000 | 90000
| CO gas consumption in stoves, Nm3/h | Nm3/h | -- | -- | -- | --
| DM water in close loop for stoves valves (3 nos.), m3/h (Hot Blast Valve) | m3/h | -- | -- | -- | -- |  | Data Received from mail dated 12.01.2022 from TFL
| NSR for PIG Iron (Rs./t) | Rs./t | 27172 | 24776 | 21829 | 24592.3333 | Received from BSL on whatsapp | NSR of Pig Iron for the period Apr'21 to Sept'21 |  |  | 36956
| VC for PIG Iron (Rs./t) |  | 19215 | 17775.04 | 15018.09 | 17336.0433 | Actual cost data from BSL | Actual variable cost of pig iron for the period of Apr'21 to Sep'21 |  |  | 19105
| Productivity | t/m3/d (WV) | 1.525 | 1.608 | 1.57 | 1.5677
Benefits to be considered on account of HBT rise:
|  |  | Base case | Proposed | Incr/ Decr
| Production | tpd | 2760.06 | 2919.0395 | 158.9795 | 2% increase in production for every 100 oC HBT increase
| Coke Rate | kg/tHM | 453 | 409.9469 | -43.0531 | 3.3% decrease in coke rate for every 100 oC HBT increase
| HBT | Deg C | 912 | 1200 | 288 | Increase in HBT due to upgradation of stoves by globally reputed design
Effect of top pressure
1 | Top Pressure (Base Case) | Kg/cm2g | 0.86
2 | Top Pressure (Proposed case) | kg/cm2g | 1
3 | Increase in productivity due to top pressure change | % | 1.54% | 1.1% increase in production for every 0.1 kg/cm2 increase in top pressure
4 | Decrease in coke rate due to top pressure change | % | 0.7% | 0.5% decrease in coke rate for every 0.1 kg/cm2 increase in top pressure
| In Proposed Case: |  |  | Existing
1 | Additional power consumption(net) : | kW | 0
2 | Additional secondary industrial water: | m3/h | 0
3 | Additional nitrogen consumption: | Nm3/h | 0
4 | Total Steam Consumption in proposed case | tph | 10 | 4 | 6
5 | Total BF gas consumption in stoves in proposed case | Nm3/h | 110000 | 90000 | 20000
6 | Total CO gas consumption in stoves in proposed case | Nm3/h | 0
7 | Total DM water in close loop for stoves valves (3 nos.) (Hot Blast Valve) | Nm3/h | 0
Sl.No | Item | Year | NSR(Rs/t)
1 | NSR of Pig iron |  | 24592.3333 | 3 years average Received from BSL on whatsapp
2 | VC of PI | Rs/t | 19105 | average actual cost data from BSL for Apr'21 to Sep'21
3 | Budgeted Contribution of PI | Rs/t | 5487.3333
4 | VC of BF Coke | Rs/t | 23586.55 | Actual cost data from BSL Sept'21
5 | BF gas | Rs/Gcal | 1080.19 | Actual cost data from BSL Sept'21
6 | CO Gas | Rs/Gcal | 1074.07 | Actual cost data from BSL Sept'21
7 | DM Water (make-up Water)(Rs. 1000 extra to be added over Industrial water) | ThM3 | --
8 | Power | MW | 5072.7 | Actual cost data from BSL Sept'21
9 | Secondary Industrial Water (Water Circ Cost) | TC | 935.5 | Actual cost data from BSL Sept'21
10 | Secondary Industrial Water (Make up) | TC | 786.44 | Actual cost data from BSL Sept'21
10 | Nitrogen | TC | 2216.26 | Actual cost data from BSL Sept'21
11 | Yield of Pig Iron from HM | % | 93% | Actual data from BSL based on 3 years average
12 | Steam | Rs/t | 1176.36 | Actual cost data from BSL Sept'21
| Duration of BF shutdown envisaged | days | 180
| Sheduled Shutdown | days | 180
| Addl. shutdown period reqd | days | 0
| Working volume of the Furnace | Cum | 1758
| Duration of Furnace operation/ year | days | 350
Note: Production loss due to shutdown will not be considered

## cash flow (hidden)
[17 empty] | S T E E L A U T H O R I T Y OF I N D I A L I M I T E D | [20 empty] | Annexure-6.6.2-1
| Phasing of expenditure-Beneficiation Plant | [15 empty] | #REF!
| Years | Plant | Internal | External | IDC | Total fund | Total fund incl. IDC | [9 empty] | #REF! |  |  | Start of prod.
|  | cost | Resources | Borrowing | @10% | incl.IDC | Equity | Loan | MM | Loan+MM | [6 empty] | Profitability Projections | [19 empty] | Rs. in crore
[17 empty] | Item/Year | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Yr 7 | Yr 8 | Yr 9 | Yr 10 | Yr 11 | Yr 12 | Yr 13 | Yr 14 | Yr 15 | Yr 16 | Yr 17 | Yr 18 | Yr 19 | Yr 20 | Yr 21 | Yr 22 | Yr 23 |  |  | Calculation of depreciation
|  | #REF! | #REF! | #REF! | [12 empty] | Capacity Utilisation | 0% | 70% | 80% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 0% |  |  | Rate of depreciation | 15%
| 1st. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | [6 empty] | Gross Margin from operation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Year of production | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| 2nd | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | [6 empty] | Interest | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | Check | Gross Block | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 3rd | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | [6 empty] | Depreciation |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | #REF! | Depreciation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PC | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | [6 empty] | Profit Before Tax (PBT) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Net Block | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! |  |  |  |  | 34.94% | Corporate Income Tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Input Tax Credit (ITC) | #REF! | [13 empty] | 1 | [26 empty] | 95% 0f CC | #REF! | [5 empty] | #REF!
[11 empty] | #REF! | [5 empty] | Profit After Tax (PAT) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Gross Margin | Rs cr | #REF! | [13 empty] | Cumulative PAT |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Capital cost | Rs cr | #REF!
| Input Tax Credit (ITC) | Rs cr | #REF!
| CC net of ITC |  | #REF! | [14 empty] | Yr 3: Start of prod.
Cash flow statement
[17 empty] | Cash-Inflows : | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Yr 7 | Yr 8 | Yr 9 | Yr 10 | Yr 11 | Yr 12 | Yr 13 | Yr 14 | Yr 15 | Yr 16 | Yr 17 | Yr 18 | Yr 19 | Yr 20 | Yr 21 | Yr 22 | Yr 23
[17 empty] | A. Cash from operations | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[16 empty] | #REF! | B. Equity/ Internal accruals | #REF! | #REF! | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | #REF! | Loan | #REF! | #REF! | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | #REF! | Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | Sl. No. | Outflow | Inflow | Net | Cor. Tax | Net | [8 empty] | (B) Cash out-flow :
|  |  | 1 | #REF! |  | #REF! | #REF! | #REF! | [8 empty] | Capital expenditure
|  |  | 2 | #REF! | #REF! | #REF! | #REF! | #REF! | [8 empty] | Equity/ Internal accruals | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 3 |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | Loan | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4 |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | Interest payment
|  |  | 5 |  | #REF! | #REF! | #REF! | #REF! | [5 empty] | Term loan | 10% |  | Long term loan | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 6 |  | #REF! | #REF! | #REF! | #REF! | [5 empty] | WC loan | 10% |  | Working Capital
|  |  | 7 |  | #REF! | #REF! | #REF! | #REF! | [7 empty] | #REF! | Principal repayment | Yr 1: 0; Yr 4: #REF!; Yr 5: #REF!; Yr 6: #REF!; Yr 7: #REF!; Yr 8: #REF!; Yr 9: #REF!; Yr 10: #REF!; Yr 11: #REF!; Yr 12: #REF!; Yr 13: #REF!
|  |  | 8 |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | Corporate Income Tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0% |  |  | 9 |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 10 |  | #REF! | #REF! | #REF! | #REF!
|  |  | 11 |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | Cash surplus | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 12 |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | Cash surplus (Cummulative) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 13 |  | #REF! | #REF! | #REF! | #REF!
|  |  | 14 |  | #REF! | #REF! | #REF! | #REF!
|  |  | 15 |  | #REF! | #REF! | #REF! | #REF! |  |  |  | Sensitivity factor | [5 empty] | Yr 3: Start of prod.
|  |  | 16 |  | #REF! | #REF! | #REF! | #REF! |  |  |  | Cap . Cost | 1 |  |  |  | NPV & IRR CALCULATIONS:
|  |  | 17 |  | #REF! | #REF! | #REF! | #REF! |  |  |  | GM | 1 |  |  |  | Item | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Yr 7 | Yr 8 | Yr 9 | Yr 10 | Yr 11 | Yr 12 | Yr 13 | Yr 14 | Yr 15 | Yr 16 | Yr 17 | Yr 18 | Yr 19 | Yr 20 | Yr 21 | Yr 22 | Yr 22
|  |  | 18 |  | #REF! | #REF! | #REF! | #REF! |  |  |  | PTC |  |  |  | A | Outflow
|  |  | 19 |  | #REF! | #REF! | #REF! | #REF! |  |  |  | Cut off. | 1 |  | #REF! | 1 | Capital Cost (excl. IDC) | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
|  |  | 20 |  | #REF! | #REF! | #REF! | #REF! | [7 empty] | 2 | Corporate Income Tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 21 |  | #REF! | #REF! | #REF! | #REF! |  |  |  | FE Parity | 1.075 |  |  | B | Inflow
|  |  | 22 |  | #REF! | #REF! | #REF! | #REF! | [7 empty] | 1 | Gross margin | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 23 |  | #REF! | #REF! | #REF! | #REF! | [7 empty] | 2 | ITC | Yr 2: #REF!; Yr 3: #REF!
[6 empty] | #REF! |  | #REF! | [7 empty] | 3 | Production loss during addl. s/d period
[6 empty] | #VALUE! |  | #VALUE! | [7 empty] | C | Net flow
[16 empty] | 1 | Pre-tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[16 empty] | 2 | Post Tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[16 empty] | D | NPV (@ 10%), Rs Cr
[16 empty] | 1 | Pre-tax | Yr 1: #REF!; Yr 22: 0; Yr 23: 0
[16 empty] | 2 | Post-tax | Yr 1: #REF!; Yr 22: 0; Yr 23: 0
[16 empty] | E | IRR
[16 empty] | 1 | Pre-tax | Yr 1: #VALUE!; Yr 22: 0%; Yr 23: 0%
[16 empty] | 2 | Post-tax | Yr 1: #VALUE!; Yr 22: 0%; Yr 23: 0%
[17 empty] | PI | Yr 1: #REF!
Pay-back period:
[17 empty] | Operating year -----> | Yr1 | Yr2 | Yr3 | Yr4 | Yr5 | Yr6 | Yr7 | Yr8 | Yr7 | Yr8
[17 empty] | Capital cost net of cenvat, Rs Cr | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | Gross margin, Rs Cr | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | Interest on loan, Rs Cr | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | Corporate tax, Rs Cr | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | Profit after int. & tax, Rs Cr | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | Balance loan, Rs Cr | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[18 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | Payback period, Yrs | Yr1: #REF!
[17 empty] | DSCR, Year-wise |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Minimum DSCR
Maximum DSCR
[17 empty] | Avg. DSCR | Yr2: #REF!

## FA (hidden)
Annexure 6.6.2-1
#REF!
#REF!
#REF!
FINANCIAL ANALYSIS
Sl. No. | Description | Unit | Value
1 | Capital Cost (Net of ITC) | Rs crore | #REF!
2 | Gross Margin | Rs crore | #REF!
3 | NPV @ 10% discount rate (Post-tax) | Rs.crore | #REF!
4 | IRR (Post-Tax) | % | #VALUE!
SENSITIVITY ANALYSIS
Sl.No | Parameter | IRR | Cap Cost
(Post-tax)
1 | Base Case | #VALUE!
2 | Capital cost up by 10% | 14.44%
3 | Gross margin less by 10% | 13.99%
4 | Combined effect of above two factors | 12.88%
5 | FE Parity +7.5% | #VALUE! | 74.4119

## CTE Rate (hidden)
Dismantling
Equipment | 10000
Structure | 8000
refrractory | 4000
Refractory
Inspection (1940 mandays) , | 10000
Erection/Ton | 6500
Equipment erection
Heating up & commisioning (3600 mandays) | 4000
Post Commisioning(3600 mandays) | 10000
Building Structure
Structure | 110000
Rail | 120000
Technological Structure
Tech. Structure | 150000
HR casting | 200000
Utility
MS Pipe (gas) | 120000
MS Pipe (water) | 110000
CI Pipe | 100000
Steam Pipe | 300000
MS compensator, water seal | 120000
Structure, support | 100000
Fabricated MS Item | 120000
SS Item | 400000

## MoM (hidden)
Record notes of meeting of the Cost Review Committee
1. Name of the Project |  | #REF!
2. Subject |  | : Revised Capital Cost Estimate & Techno-Economics (R1)
3. Assignment No. |  | : 04/DE/4747
4. Date of cost review |  | : 18.05.2022
5. Proceedings of meeting:
i. Basis for equipment only |  |  | 1EURO= | #REF! | 1 USD= | #REF! |  |  | (Forward Premium Rates)
Sl. No. | Name of the Supplier/Contractor | Scope of supply | Imported Supply |  |  |  |  | Indigenous Supply |  |  |  | Engineering estimate for additional scope of supply other than BQ/ PO |  | Total cost |  | Total cost considered (Rs in Crore): Engg. Est.
|  |  | Quoted Price |  | Normalised value (Adjusted for Cap., Escl. and excl. D&E, erection, supv. etc. if any ) | Factor for location | Price trend considered (Knocked off by) | Quoted Price | Normalised value (Adjusted for Cap., Escal. and excl. any scope like D&E, erection, Civil, Strl. etc. if any) | Factor for location | Price trend considered (BQ is already Knocked off by 10%)
|  |  | FC (in FE) | FC (Equivalent Rs. In Crore) | FC (Equivalent Rs. In Crore) |  | 0% | LC (Rs. in Crore) | LC (Rs. in Crore) | 0 | 0% | FC (Equivalent Rs. Crore) | LC (Rs. Crore) | FC (Equivt Rs. Cr) | LC (Rs. Crore)
1) Details of BQs & POs considered
a | BQ of M/s Hutni Projeckt India Ltd. dtd 15.03.2022 | Electrical exhauster of Howden make |  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF!
b | BQ of M/s Hutni Projeckt India Ltd. dtd 15.03.2023 | Spares for electrical exhauster | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF!
c | BQ of M/s Hutni Projekt Frydek Mistek (HPFM) and HPIL dtd 18.11.2021 | Naphthalene Recovery Plant | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | 10% to civil
d | BQ of M/s paul worth dated 27.01.2022 | Naphthalene Recovery Plant | 12000000 Euro | #REF! | #REF! | [9 empty] | #REF! | Not considered
e | Engineering Estimate /BQs/POs | All other items except above | [10 empty] | #REF! |  | #REF! | #REF!
| Sub total |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 0 | #REF! | #REF! | #REF!
2) Details of POs referred
a. | Contract of Acme automation at BSL-T&C(M)/A6171/PP/476 for installation of 33 Electronic WF at Sinter plant dt. 17.01.2020 | 33 electronic weigh feeder of different capacity. Individual cost of BWF of different capacity is not provided in contract. |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | Not considered
b. | PO of M/s Schenk for beltweigh scale of 1000 TPH with PO no. 313103061140/0001 dt: 19.04.2014 | Beltweigh scale of 1000 TPH | [13 empty] | Not considered
[17 empty] | #REF! | #REF!
2) Details of earlier POs considered
| NA |  |  | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
|  |  | (Rs. in Crore.) | [11 empty] | (Rs. in Crore)
ii) | Estimate considered for the Equipment of the Project= |  | #REF! |  | Estimate considered during previous issue of capital cost (base date 3rd Quarter 2020)= | [9 empty] | 164.1064
iii) | Reasons for selecting above cost:
a) | The committee noted that the previous Capital cost estimate for subject project was Rs. 390.46 Cr net of ITC ( base date of 3rd Quarter 2020) which was based primarily on Engineering estimates, BQs/POs. However, a large part of the engineering estimate was based on previous projects of rebuilding of COB with suitable escalations.
b) | Committee discussed on BOQ along with cost & supporting documents submitted by TFL and concerned TFM members .
c) | For supply cost of equipment, BQ, PO & engg estimates for the equipment mentioned at Sl. No. a ,b,c & e have been considered. Cost review committee noted that as per practice for coke oven battery, capital cost estimate for the subject project has been prepared primarily on the basis of engineering estimate. However, a large part of the engg est is based on recently ordered values of COB#2, RSP and capital cost estimate for COB#6 at BSL ( 02/4099, Cost Committee on 08.09.2021) with suitable escalations.
d) | Impact on total basic cost due to change in scope of subject project from previous estimate of capital cost is Rs. 60.58 Cr. Details of change in scope and its impact on basic cost is attached.
e) | Cost committee noted that after accounting for change in scope and its associated cost, basic cost escalation due to time lapse is about 43% considering the current market scenario and location fator from previous issue of capital cost (base date 3rd Quarter 2020).
f) | Refractory cost is based on various latest BQs with escalation for time lapse. Cost committee delibrated to knockdown Silica bricks & Mortar cost by 15% which is based on BQ of M/s OCL Dalmia Refractories dated 31.12.2021 as it's cost appeared on higher side.
g) | Erection cost of refractory is based on engineering estimate instead of normative provisions. Rate of Inspection of refractory is considered as Rs.10000/Manday for 1940 mandays and rate of refractory erection is considered Rs. 6500/Ton.
h) | Rs. 5.04 Cr over and above normative provisions has been considered towards equipment erection for heating up, commissioning and post commissioning charges.
i) | Oven machines (Pkg-2) cost are based on discussion of TFM (Mech.) held with M/s BEC. It concluded that rate should be about 35% raised over order price for COB#2, RSP Oven machines. As the order price of RSP is above 10% more than estimate hence, the cost committee decided to increase basic rate for subject project by 45% over rate considered for COB#2 RSP.
J) | Civil works cost has been prepared on the basis of DSR 2021. Cost committee noted that cost of civil works in previous capital cost estimation was based on DSR 2018.
k) | Electrical cost estimation is based on engg estimate based on BQs/Pos and M/s. Havells price list of DEC-2021(with 20 % discount).
l) | P.C.&A. cost estimation considered engg. Estimate , recent BQs with 10% discount and previous BQs/POs with suitable escalation on the basis of WPI (all commodities).
m) | Cost committee considered structure/pipes rate as prevailing market rate. Rate for Heat resistant casting is based on lead section discussion with M/s Mecon.
iv) | Complete scope:
Sl. No. | Description | Basic Cost |  |  | Factor for location/ Area of difficulty | Total | Remarks
|  | FC (Eq Rs. in Crore) | LC (Rs. In crore)
1 | Equipment + Tech structure | #REF! | #REF! |  |  | #REF! | brought from the above
2 | Civil |  | #REF! |  | #REF! | #REF! | DSR 2021
3 | Structural | #REF! | #REF! |  | #REF! | #REF!
4 | Refarctories | #REF! | #REF! |  | #REF! | #REF! | Based on BQs
5 | Spares | #REF! | #REF! |  | #REF! | #REF!
6 | Erection and Commissioning |  | #REF! |  | #REF! | #REF! | Normative+add. Prov. for heating etc
7 | Engineering & Construction | #REF! | #REF! |  | #REF! | #REF! | 2.5% for owner, 5.0% for contractor
8 | Taxes & Duties incl. Frt | #REF! | #REF! |  | #REF! | #REF!
9 | Foreign Supervision | #REF! |  |  | #REF! | #REF!
10 | Foreign Training | #REF! | 0 |  | #REF! | #REF!
10 | CER & Env. Clearance |  | #REF! |  |  | #REF!
11 | Contingency | #REF! | #REF! |  | #REF! | #REF! | @5%
12 | Other (IDC) |  | #REF! |  |  | #REF!
14 | ITC |  | #REF! |  |  | #REF!
| Total | #REF! | #REF! |  |  | #REF!
v. TFL confirmed that the BOQ considered for preparing capital cost is for the total scope of work for the subject project.
vi. Implementation schedule : 37 months (from stage-II approval). Cost committee noted that implementation schedule was 30 months from stage-II during previous capital cost estimation
vii. Capital cost estimate: |  |  |  |  | (Rs. in Crore.) | [9 empty] | (Rs. in Crore)
Based on the above considerations, capital cost estimate net of ITC for the subject project = |  |  |  |  | #REF! |  |  | Capital cost estimate net of ITC for the subject project during previous issue of capital cost (base date 3rd Quarter 2020) = | [6 empty] | 390.4616
The committee deliberated on the above issues and found the same in order.
6. Following officials were present:
Sl. No. | Name | Designation | Signature
i | Mr. S Joardar | CGM & I/ c (Projects and C& S) -Chairman
ii | Mr. M. Choudhary | CGM (I&S, Steel, Rolling Mills and C.C &C)
iii | Mr. Ajay Kumar | CGM (Mechanical and U&S)
iv | Mr. Shalabh Sharma | CGM (Projects-PFC, BE, CTE, C&C & IPSS)
v | Mr. Sanjay Kumar | CGM (PC&A, Elec., C& IT)
vi | Mr. Manoj Mishra | GM & I/c (CTE)-Convenor
vii | Mr. S. Bhattacharjee | GM & I/c (C.C.&C.)
viii | Ms. Jyoti Dayal | GM (C.C.&C.)
ix | Mr. Anup Kumar | AGM (Proj-CTE)
x | Mr. R. Kashyap | Sr. Mgr. (Proj-CTE)
Also committee decided to discount recent BQs by 5%. In addition to above, committee decided to load 10% of Equipment cost on equipment for Risks, Financial Charges, and Overheads of contractor.

## Pkg Cost (hidden)
CONFIDENTIAL
Ref. No.: CET-17(4)/4004/ 31
Date: 04.02.2015
STEEL AUTHORITY OF INDIA LIMITED
#REF!
#REF! | Augmentation of facilities to supply rails for Iran export order
PACKAGE COST ESTIMATE
TS NO.: CET/01/BH/4004/TS/ME/01/R=1
| 1 EURO=Rs. | 75 |  | Rs. Crore
| 1 USD=Rs. | 68
Sl.No. | Description of Item | FC | LC | Total
1 | Design & Engineering incl. drgs. & doc. | #VALUE! | #VALUE! | #VALUE!
2 | Supply of Plant & Equipment Incl. Technological Structures | #REF! | 0 | #REF!
3 | Supply of Building steel structures including sheeting and glazing |  | 0 | 0
4 | Supply of Refractories | #REF! | 0 | #REF!
5 | Civil Engineering Work including all related supplies- for equipment foundation |  | 0.059 | 0.059
6 | Civil Engineering Work including all related supplies- Others including dismantling |  | #VALUE! | #VALUE!
7 | Storage, handling, Erection of Plant & eqpt, Bldg. steel structure & Refractories incl. Comm. & PG tests of the facilities |  | #REF! | #REF!
8 | Foreign supervision charges in India during erection, startup, commissioning & PG test for _____mandays | #REF! |  | #REF!
9 | Foreign Training charges for _____mandays | #REF! |  | #REF!
10 | Ocean Freight, Custom, port clearance & inland transport for imported items | #REF! | #REF! | #REF!
11 | Comprehensive Marine / transit & Storage-cum-erection insurance | Included above
12 | Sub-total (1 to 11) | #VALUE! | #VALUE! | #VALUE!
13 | Purchaser's Scope: | 0 | [7 empty] | 0
i | BCD @7.5% on CIF |  | #REF! | #REF!
ii | Social welfare surcharge @ 10% on BCD |  | #REF! | #REF!
iii | GST @ 18 % on imported supply |  | #REF! | #REF!
iv | Income Tax @ 10 % grossed-up on imported services |  | #VALUE! | #VALUE!
v | GST @ 18 % on imported Services & IT |  | #VALUE! | #VALUE!
| Sub-total (13) | 0 | #REF! | #REF!
14 | Total Package Cost | #VALUE! | #REF! | #REF!
15 | Input tax credit (ITC) on GST |  | #VALUE! | #VALUE!
16 | Package cost net of ITC on GST | #VALUE! | #REF! | #REF!
(P. K. Mishra)
AGM (Projects-CTEB)
SAIL/CET
| 1 EURO=Rs. | 75 | 13.05.2016
| 1 USD=Rs. | 68 | -do
| Erection for imported supply | 6%
| Erection for plant & equipt | 12%
| Erection for structure | 20% | [5 empty] | Rs. Cr.
| Erection for refractory | 12%
| CD | 7.5%
Sl.No | Item | Basic cost |  | Indigenous supplies & services
|  | Imp. Items | Indg. Items | GST Ind. supply | GST Ind. services | Inland Frt & Ins | Purchaser's scope | Total
| #REF! | #REF! | #REF! | 18% | 18% | 18%
1 | Design & Engineering | #VALUE! | #VALUE! |  | #VALUE! |  |  | #VALUE!
2 | Supply of Plant & eqpt | #REF! | 0 | 0 |  | 0 |  | #REF!
3 | Supply of SW | #REF! | 0 | 0 |  | 0 |  | #REF!
4 | Supply of Tech Strs | #REF! |  | 0 |  | 0 |  | #REF!
5 | Building structures |  | 0 | 0 |  | 0 |  | 0
6 | Refractories | #REF! |  | 0 |  | 0 |  | #REF!
7 | Civil work incl. all related supplies -Others |  | 0 |  | 0 |  |  | 0
| Civil work incl. all related supplies - Equipment foundation |  | 0.05 |  | 0.009 |  |  | 0.059
| Dismantling |  | #VALUE! |  | #VALUE! |  |  | #VALUE!
8 | Erection of Plant & eqpt |  | #REF! |  | #REF! |  |  | #REF!
| Erection of Tech Strs, |  | #REF! |  | #REF! |  |  | #REF!
| Erection of build. strs |  | 0 |  | 0 |  |  | 0
| Erection of Refractories |  | #REF! |  | #REF! |  |  | #REF!
9 | Foreign Supervision | #REF! | [5 empty] | #REF!
10 | Training | #REF! | [5 empty] | #REF!
11 | a) Ocean Freight | #REF! |  |  |  | #REF! |  | #REF!
| b) Custom, port clearance & inland trasport | [5 empty] | #REF! | #REF!
12 | Purchaser's scope | [5 empty] | #REF! | #REF!
| Total | #VALUE! | #VALUE! | 0 | #VALUE! | #REF! | #REF! | #VALUE! | 250.1109
| ITC |  |  | 0 | #VALUE! | #REF! | #REF! | #VALUE! | 19.5742
[8 empty] | #VALUE! | 230.5368
0
0

## Pi Chart (hidden)
1 | Equipment | 0
| Refractory | 0
| Structure | 0
| CIVIL | 0
| Spares | 0
| Dismantling & Re-erection | 0

## Pie Chart (hidden)
Rs. Cr.
Mechanical | #REF!
Utilities | #REF!
Electrical | #REF!
Process Control and Automation | #REF!
Technological Structure | #REF!
Building Structure | #REF!
Refractories | #REF!
Civil Eq Foundation | #REF!
Civil others | #REF!
Rs. Cr.
Mechanical | #REF!
Technological Equipments
Utilities | #REF!
Electrical | #REF!
Process Control and Automation | #REF!
C&IT
Technological Structure | #REF!
Building Structure | #REF!
Refractories | #REF!
Civil Eq Foundation | #REF!
Civil others | #REF!

## Scope change from R0 (hidden)
Annexure to MOM dated 18.05.2021
Scope Change from R0 to R1
| Item | Unit | Quantity | Rate | Amount (Rs. in Lakh)
1 | Hydrojet Cleaner | Nos | 1 | #REF! | #REF!
2 | Battery operated vehicle | Nos | 1 | #REF! | #REF!
3 | Pusher side & Coke side service platform of Refractory Paving in place of Cast Iron Paving |  | 1 | -696000 | -6.96
4 | #REF! | M | #REF! | #REF! | #REF!
5 | Bench Vice | Nos | 1 | #REF! | #REF!
6 | Roughing and grinding machine | Nos | 1 | #REF! | #REF!
7 | Drilling Machine | Nos | 1 | #REF! | #REF!
8 | Underslung crane inplace of manual winch | Nos | 1 | #REF! | #REF!
9 | #REF! | Nos | 1 | 83820302.1516 | 838.203
10 | Conveyor galleries dismantling | MT | 550 | #REF! | #REF!
11 | Coveyor galleries new fabrication | MT | 550 | #REF! | #REF!
12 | Upgradation of rail | MT | 90 | #REF! | #REF!
13 | #REF! | Nos | 2 | #REF! | #REF!
14 | #REF! | MT | #REF! | #REF! | #REF!
15 | Electrical Addition |  |  |  | #REF!
16 | Electrical Deletion |  |  |  | -132
17 | #REF! | Nos. | 1 | #REF! | #REF!
18 | #REF! | Nos. | 1 | #REF! | #REF!
19 | #REF! | Nos | 1 | #REF! | #REF!
| Sub Total (Equ.+ Structure + Refractory) |  |  |  | #REF!
20 | Civil |  |  |  | 1730.0705
Total (Rs. In Cr) |  |  |  |  | #REF!
| NRU basis changed to BQ from Engg estimate resulting in differnce |  |  |  | 3369

## Civil scope change from R0 (hidden)
Civil works |  |  | Qty | Rate | Amt (Rs. in Lakh)
1 | Excavation | Cum | 13331 | 473.3043 | 63.0962
2 | PCC M10 | Cum | 349 | 7253.1739 | 25.3136
3 | RCC-M25 | Cum | 5619 | 11410.3478 | 641.1474
4 | Non-Shrink Grout | Cum | 5 | 50000 | 2.5
5 | HRC M30 | Cum | 60 | 13623.0217 | 8.1738
6 | Reinforcement | MT | 767 | 77956.5217 | 597.9265
8 | Inserts | MT | 8 | 100000 | 8
10 | IPS Flooring | Sqm | 720 | 473.913 | 3.4122
14 | Brickwork -full brick | Cum | 569 | 7317.087 | 41.6342
15 | 20mm thk plaster | Sqm | 1824 | 349.6957 | 6.3784
16 | 15mm thk plaster | Sqm | 1604 | 295.3913 | 4.7381
17 | 6mm thk plaster | Sqm | 2772 | 253.05 | 7.0145
18 | Weatherproof paint | Sqm | 1824 | 213.0435 | 3.8859
19 | Whitewashing | Sqm | 4320 | 28.2174 | 1.219
20 | Boulder Soling | Cum | 180 | 1562.8696 | 2.8132
21 | APP | Sqm | 696 | 490 | 3.4104
22 | Steel Doors | Sqm | 19 | 7234.8261 | 1.3746
23 | Windows | Sqm | 31 | 7234.8261 | 2.2428
25 | False floor | Sqm | 24 | 4701.8696 | 1.1284
27 | RCC/PCC Dismantling | Rm | 2176 | 2546.1739 | 55.4047
32 | Piling (600 dia) | Rm | 4056 | 3413.535 | 138.453
33 | DPC | Sqm | 32 | 322.4783 | 0.10319
34 | Plinth Protection | Sqm | 70 | 592.7391 | 0.41492
35 | False Ceiling | Sqm | 684 | 1582.6522 | 10.8253
52 | Diamond Wire Saw cutting | Sqm | 20 | 6000 | 1.2
53 | Vibration Isolation System (Spring) | Rupees | 1 | 800000 | 8
54 | PVC tiles | Sqm | 684 | 1500 | 10.26
55 | SS inserts | MT | 13 | 400000 | 52
29 | Rail tracks Laying | Rm | 80 | 30000 | 24
30 | Rail tracks Dismantling | Rm | 80 | 5000 | 4
|  |  |  | Total | 1730.0705

## PBE_Pkg-1
Annexure-1
CONFIDENTIAL
Ref. No.: CET-17(4)/4747/159
Date: 14.07.2023
STEEL AUTHORITY OF INDIA LIMITED
DURGAPUR STEEL PLANT
Rebuilding of COB#4 (Package-1, Battery Proper)
PRICE BID EVALUATION
Comparative statement of the quoted prices w.r.t. estimate
[7 empty] | 1 Euro= |  | 90.4798
Sl. No. | Description of Item |  |  | Estimate | BEC & Consortium | [11 empty] | MECON Limited
[5 empty] | Original Price | [5 empty] | Final Price after decrement | [5 empty] | Original Price | Final Price after decrement
[5 empty] | M/s GPK |  | M/s CUI |  | M/s BEC | FC+LC (₹ Crore) | M/s GPK |  | M/s CUI |  | M/s BEC | FC+LC (₹ Crore) | Total (₹ Crore) | Total (₹ Crore)
[5 empty] | FC (Euro) | Equivalent ₹ (Crore) | FC (Euro) | Equivalent ₹ (Crore) | LC ₹ (Crore) |  | FC (Euro) | Equivalent ₹ (Crore) | FC (Euro) | Equivalent ₹ (Crore) | LC (₹ Crore)
|  | FC | LC | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total
1 | Design & Engineering | 0 | 25.7204 | 25.7204 | 7200000 | 7200000 | 2500000 |  | 1.416 | 89.1814 | 2700000 | 24.4295 | 1700000 | 15.3816 | 0.118 | 39.9291 | 45.7139 | 29.5325
2 | Supply of Plant & Equipment Incl. Technological Structures | 0 | 274.3778 | 274.3778 |  |  |  |  | 691.48 | 691.48 |  | 0 |  | 0 | 336.1466 | 336.1466 | 519.1438 | 419.1602
3 | Supply of Building steel structures including sheeting and glazing |  | 41.0941 | 41.0941 |  |  |  |  | 3.776 | 3.776 |  | 0 |  | 0 | 3.776 | 3.776 | NA | NA
4 | Supply of Refractories | 0 | 90.1902 | 90.1902 |  |  |  |  | 177 | 177 |  | 0 |  | 0 | 129.8 | 129.8 | 120.5456 | 107.1596
5 | Civil Engineering Work including all related supplies- for equipment foundation |  | 46.5077 | 46.5077 |  |  |  |  | 70.8 | 70.8 |  | 0 |  | 0 | 70.8 | 70.8 | 97.7041 | 90.5624
6 | Civil Engineering Work including all related supplies- Others |  | 14.0089 | 14.0089 |  |  |  |  | 23.6 | 23.6 |  | 0 |  | 0 | 23.6 | 23.6 | 5.31 | 5.31
7 | Storage, Handling, Erection (including dismantling ) of Plant & Equipments & Refractories including Commisioning and PG tests of the facilities |  | 60.686 | 60.686 |  |  |  |  | 158.12 | 158.12 |  | 0 |  | 0 | 94.4 | 94.4 | 109.2956 | 90.6546
8 | Storage, Handling and Erection of Building Steel Structures |  | 7.5402 | 7.5402 |  |  |  |  | 2.36 | 2.36 |  | 0 |  | 0 | 2.36 | 2.36 | NA | NA
9 | Foreign Supervision charges in India during erection, startup, commissioning and PG test for ____mandays | 0 |  | 0 | 800000 |  | 1000000 |  |  | 16.2864 | 750000 | 6.786 | 648000 | 5.8631 |  | 12.6491 | NA | NA
10 | Training charges: (a) For ___________ Foreign mandays, (b) For ___________Indian mandays | 0 |  | 0 |  |  | 200000 |  |  | 1.8096 |  | 0 |  | 0 |  | 0 | 0.118 | 0.118
11 | Customs, Port clearance (excluding duties & cess to be paid by Employer) and Inland transportation (for all items quoted in foreign currency) | 0 | 0 | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 | NA | NA
12 | Comprehensive Marine / transit & Storage-cum-erection insurance |  | Included above | Included above |  |  |  |  | 0.472 | 0.472 |  | 0 |  | 0 | 0.354 | 0.354 | 3.5589 | 2.5739
13 | Supply of 2 years O & M spares | 0 | 0 | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 | 0
14 | Total Quoted Price (1 to 13) | 0 | 560.1253 | 560.1253 | 8000000 | 7200000 | 3700000 | 0 | 1129.024 | 1234.8854 | 3450000 | 31.2155 | 2348000 | 21.2447 | 661.3546 | 713.8148 | 901.39 | 745.0711
15 | Purchaser's Scope: | 0 | [16 empty] | 0
i | BCD @7.5% on CIF |  | 0 | 0 | 0 |  | 0 |  | 0 | 6.5824 | 0 |  | 0 |  | 0 | 2.9858
ii | Social welfare surcharge @ 10% on BCD |  | 0 | 0 | 0 |  | 0 |  | 0 | 0.65824 | 0 |  | 0 |  | 0 | 0.29858
iii | GST @ 18 % on imported supply |  | 0 | 0 | 0 |  | 0 |  | 0 | 17.1011 | 0 |  | 0 |  | 0 | 7.7572
iv | Income Tax @ 10 % grossed-up on imported services |  | 0 | 0 | 0 |  | 0 |  | 0 | Included | 0 |  | 0 |  | 0 | Included
v | GST @ 18 % on imported Services & IT |  | 0 | 0 | 0 |  | 0 |  | 0 | 3.2573 | 0 |  | 0 |  | 0 | 2.2768
| Sub-total (15) | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 27.599 | 0 |  | 0 |  | 0 | 13.3184
16 | Total Evaluated Price (14 to 15) | 0 | 560.1253 | 560.1253 | 8000000 | 7200000 | 3700000 | 0 | 1129.024 | 1262.4844 | 3450000 | 31.2155 | 2348000 | 21.2447 | 661.3546 | 727.1332 | 901.39 | 745.0711
17 | Input tax credit (ITC) on GST |  | 75.7571 | 75.7571 |  |  |  |  | 167.688 | 188.0464 |  |  |  |  | 96.3486 | 106.3826 | 136.6902 | 112.8449
18 | Total Evaluated Price net of ITC on GST | 0 | 484.3682 | 484.3682 |  |  |  |  | 961.336 | 1074.438 |  |  |  |  | 565.006 | 620.7506 | 764.6998 | 632.2262
19 | Variation w.r.t. Estimate (in %) | [8 empty] | 121.8% | [5 empty] | 28.16% | 57.88% | 30.53%
20 | Ranking | [9 empty] | L1 | [6 empty] | L2
[14 empty] | Consortium decrement (₹ Crore) | 396.33 |  | Mecon decrement (₹ Crore) | 132.4736
[14 empty] | Consortium decrement (Euro) | 5902000