## Basic cost (1) (hidden)
Revamping of WG#1 & HG#6 Manual Roll Grinding Machine to CNC Roll Grinding Machine
| ASSIGN. NO.- 05/DE/5043 |  |  | 1EURO=Rs.(with forward premium rate) |  | 1USD=Rs.(with forward premium rate) |  | 07.07.2023
| Main Package | Unit | Qty. | Unit Rate (LC)- Rs.L | Amt. (Rs. L) LC | Rate (FC) | Amt. (Rs. L) FC | Basis / Remarks | CTE Remarks
Technological equipment
| Revamping & CNC Retrofitting of WG-1 including Mech,Electr & PCA | Nos. | 1 | 1427 | 1427 |  |  | BQ-Maxis Motion, dt.23/03/2023 | It should be only supply rate here. Erection and commisioning should be in different head. Please review. | 1300
| Revamping & CNC Retrofitting of HG-6 including Mech,Electr & PCA | Nos. | 1 | 921 | 921 |  |  | BQ-Maxis Motion dt. 23/03/2023 | -do-
| Sub-total Technological equipment |  |  |  | 2348
Mechanical
| Air Conditioning 2T- Split Type, for MCC Panel rooms for WG-1 & HG-6 | Nos. | 5 | 0.5 | 2.5 |  |  | Market Price | Please elaborate on basis
| Sub-total Mechanical |  |  |  | 2.5
Electrics
| Automatic Voltage Regulator | Unit | 2 | 10 | 20 |  |  | Price from Cost Database | enggineering estimate or BQ/PO?
| UPS- 7.5kVA | Unit | 2 | 10 | 20 |  |  | Price from Cost Database | enggineering estimate or BQ/PO?
| Incomer Cable to MCC (300m) | Unit | 2 | 22.095 | 44.19 |  |  | Havells Price List Jan 2023 with 25% discount
| Earthing | Unit | 2 | 5 | 10 |  |  | Engineering Estimate based on the Electrical cost database
| Sub-total Electrics |  |  |  | 94.19
| Total : Plant & Equipment |  |  |  | 2444.69 |  | 0
| CIVIL WORKS |  |  | Unit Rate (LC) Rs. | Amt. (Rs. L) LC |  |  |  | Please clarify if item is in Civil (Others or Equip. foundation)
| Existing Civil fdn. Cleaning ,chipping,grouting, etc. including coolant base work for bigger tank | Nos. | 2 | 5 | 10 |  |  | Engg.Est
| Refurbishing existing MCC panel Rooms | Nos. | 2 | 6 | 12 |  |  | Engg.Est
| Total : Civil ( Others or Equip. foundation) |  |  |  | 82.9131 |  | 0
| MISCELLANEOUS | [6 empty] | DSR 2021
18 | Dismantling of Concrete (RCC) | Cum | 1300 | 2546.1739 | 33.1003 |  |  | 15.3 | Please clarify if item is in Civil (Others or Equip. foundation) or in some other head.
19 | Dismantling of Brickwork | Cum | 1500 | 1476.5217 | 22.1478 |  |  | 15.7.4 | -do-
20 | Transportation of Building Debris (Upto 5Km) | Cum | 3000 | 188.8348 | 5.665 |  |  | 1.1.1 (Page No.82, Vol.1) | -do-
Dismantling
| Structure Dismantling | t | 50 | 8000 | 0.04 |  |  | engg. estimate
| Sheeting Dismantling | m2 | 300 | 150 | 0.0045 |  |  | engg. estimate
| Total dismantling |  |  |  | 0.0445 |  | 0

## Basic cost(Rev) (hidden)
Revamping of WG#1 & HG#6 Manual Roll Grinding Machine to CNC Roll Grinding Machine
| ASSIGN. NO.- 05/DE/5043 |  |  | 1EURO=Rs.(with forward premium rate) |  | 1USD=Rs.(with forward premium rate) |  | 07.07.2023
| Main Package | Unit | Qty. | Unit Rate (LC)- Rs.L | Amt. (Rs. L) LC | Rate (FC) | Amt. (Rs. L) FC | Basis / Remarks |  | CTE Remarks
| Technological equipment | [6 empty] | 1st. BQ- MAXIS MOTION | 2nd. BQ- CNC-DESIGN Not Considered | Please include additional reference from alternate BQ in BOQ.
| Revamping & CNC Retrofitting of WG-1 including Mech,Electr & PCA | Nos. | 1 | 1300 | 1274.5098 |  |  | Supply of Eqpt.BQ-Maxis Motion, dt.23/03/2023. 2% freight has been factored out | Euro 1,680,000 | If required, erection and commisioning provided in BQ may be considered. It should be in different head of BOQ to consider it. | 1300
| Revamping & CNC Retrofitting of HG-6 including Mech,Electr & PCA | Nos. | 1 | 824 | 807.8431 |  |  | Supply of Eqpt. BQ-Maxis Motion, dt.23/03/2023. 2% freight has been factored out | Euro 1,090,000 | -do- | 824
| Sub-total Technological equipment |  |  |  | 2082.3529
Mechanical
| Air Conditioning 2T- Split Type, for MCC Panel rooms for WG-1 & HG-6 | Nos. | 5 | 0.5 | 2.5 |  |  | Market Price- Enquired at New Digital World-Dealer of Voltas at Rourkela |  | Please elaborate on basis
| Sub-total Mechanical |  |  |  | 2.5
Electrics
| Automatic Voltage Regulator | Unit | 2 | 10 | 20 |  |  | Engg. Est-Cost Data base |  | enggineering estimate or BQ/PO?
| UPS- 7.5kVA | Unit | 2 | 10 | 20 |  |  | Engg. Est-Cost Data base |  | enggineering estimate or BQ/PO?
| Incomer Cable to MCC (300m) | Unit | 2 | 22.095 | 44.19 |  |  | Havells Price List Jan 2023 with 25% discount
| Earthing | Unit | 2 | 5 | 10 |  |  | Engineering Estimate based on the Electrical cost database
| Sub-total Electrics |  |  |  | 94.19
| Total : Plant & Equipment |  |  |  | 2179.0429 |  | 0
| CIVIL WORKS ( Eqpt. Fdn.) |  |  | Unit Rate (LC) Rs. | Amt. (Rs. L) LC
| Existing Civil fdn. Cleaning ,chipping,grouting, etc. including coolant base work for bigger tank | Nos. | 2 | 5 | 10 |  |  | Engg.Est | EQPT. Fdn.
Earlier provided DSR items are missing in BOQ. Please confirm.
| Sub Total : Civil ( Equip. foundation) |  |  |  | 10 |  | 0
CIVIL WORKS (Others)
| Refurbishing existing MCC panel Rooms | Nos. | 2 | 6 | 12 |  |  | Engg.Est | Other than Eqpt.Fdn.
| Sub Total : Civil ( Others) |  |  |  | 12
Dismantling
| WG-1 | T | 50 | 12000 | 0.06 |  |  | engg. estimate |  | CTE rate for dismantling technological equip.
| HG-6 | T | 30 | 12000 | 0.036 |  |  | engg. estimate |  | -do-
| Total dismantling |  |  |  | 0.096 |  | 0
| Transportation of Critical parts of both machines to Pune Works & back | Trips | 5 | 4 | 20 |  |  | Engg, Est . Per Trip by Trailor 10-12 T and 5 Trips for 50T |  | please elaborate!
ERECTION AND COMMISSIONING
| WG-1 | Nos. | 1 | 127 | 127 |  |  | As per BQ of Maxis Motion | Euro 155000.00(CNC Design)
| HG-6 | Nos. | 1 | 97 | 97 |  |  | As per BQ of Maxis Motion | Euro 130000.00(CNC Design)
| TOTAL |  |  |  | 224

## Basic cost (Received Post Dr) (hidden)
Revamping of WG#1 & HG#6 Manual Roll Grinding Machine to CNC Roll Grinding Machine
| ASSIGN. NO.- 05/DE/5043 |  |  | 1EURO=Rs.(with forward premium rate) |  | 1USD=Rs.(with forward premium rate) |  | 07.07.2023
| Main Package | Unit | Qty. | Unit Rate (LC)- Rs.L | Amt. (Rs. L) LC | Rate (FC) | Amt. (Rs. L) FC | Basis / Remarks |  | CTE Remarks
| Technological equipment | [6 empty] | 1st. BQ- MAXIS MOTION, Pune, dt.23/03/2023 Considered | 2nd. BQ- CNC-DESIGN, Thailand, dt.07/06/2023 Not Considered | Please include additional reference from alternate BQ in BOQ.
[8 empty] | Supply with revamping Mechanical, Electrical & CNC retrofitting of the Roll Grinding machine WG-1 & HG-6 | Supply with revamping Mechanical, Electrical & CNC retrofitting of the Roll Grinding machine WG-1 & HG-6
[8 empty] | Price in INR at pg.5 | Price in EURO at pg.8
| Revamping & CNC Retrofitting of WG-1 including Mech,Electr & PCA | Nos. | 1 | 1300 | 1274.5098 |  |  | Supply of Eqpt.BQ-Maxis Motion, 2% freight has been factored out | Euro 1,680,000 | If required, erection and commisioning provided in BQ may be considered. It should be in different head of BOQ to consider it. | 1300
| Revamping & CNC Retrofitting of HG-6 including Mech,Electr & PCA | Nos. | 1 | 824 | 807.8431 |  |  | Supply of Eqpt. BQ-Maxis Motion, 2% freight has been factored out | Euro 1,090,000 | -do- | 824
| Sub-total Technological equipment |  |  |  | 2082.3529
Mechanical
| Air Conditioning 2T- Split Type, for MCC Panel rooms for WG-1 & HG-6 | Nos. | 5 | 0.5 | 2.5 |  |  | Market Price- Enquired at New Digital World-Dealer of Voltas at Rourkela |  | Please elaborate on basis
| Sub-total Mechanical |  |  |  | 2.5
Electrics
| Automatic Voltage Regulator | Unit | 2 | 10 | 20 |  |  | Engg. Est-Cost Data base |  | enggineering estimate or BQ/PO?
| UPS- 7.5kVA | Unit | 2 | 10 | 20 |  |  | Engg. Est-Cost Data base |  | enggineering estimate or BQ/PO?
| Incomer Cable to MCC (300m) | Unit | 2 | 22.095 | 44.19 |  |  | Havells Price List Jan 2023 with 25% discount | To be deleted as per DR
| Earthing | Unit | 2 | 5 | 10 |  |  | Engineering Estimate based on the Electrical cost database
| Sub-total Electrics |  |  |  | 94.19
| Total : Plant & Equipment |  |  |  | 2179.0429 |  | 0
| CIVIL WORKS ( Eqpt. Fdn.) |  |  | Unit Rate (LC) Rs. | Amt. (Rs. L) LC
| Existing Civil fdn. Cleaning ,chipping,grouting, etc. including coolant base work for bigger tank | Nos. | 2 | 4 | 8 |  |  | Engg.Est | EQPT. Fdn. Confirmed with HOD(Civil) & changed from 10 to 8 Lakhs
Earlier provided DSR items are missing in BOQ. Please confirm.
| Sub Total : Civil ( Equip. foundation) |  |  |  | 10 |  | 0
CIVIL WORKS (Others)
| Refurbishing existing MCC panel Rooms | Nos. | 2 | 3.5 | 7 |  |  | Engg.Est | Other than Eqpt.Fdn. Confirmed with HOD Civil & changed from 12 to 7 lakhs
| Sub Total : Civil ( Others) |  |  |  | 7
Dismantling
| WG-1 | T | 50 | 12000 | 0.06 |  |  | engg. estimate |  | CTE rate for dismantling technological equip.
| HG-6 | T | 30 | 12000 | 0.036 |  |  | engg. estimate |  | -do-
| Total dismantling |  |  |  | 0.096 |  | 0
| Transportation of Critical parts of both machines to Pune Works & back | Trips | 5 | 4 | 20 |  |  | Engg, Est . Per Trip by Trailor 10-12 T and 5 Trips for 50T |  | please elaborate!
| ERECTION AND COMMISSIONING | [7 empty] | Installation and Commissioning as per CNC Design
| WG-1 | Nos. | 1 | 127 | 127 |  |  | As per BQ of Maxis Motion | Euro 155000.00
| HG-6 | Nos. | 1 | 97 | 97 |  |  | As per BQ of Maxis Motion | Euro 130000.00
| TOTAL |  |  |  | 224

## GM (hidden)
Annexure -6.5.1-1
BOKARO STEEL PLANT
Installation of 4th Stove and Revamping of existing 3 nos. of Stoves in BF#2
GROSS MARGIN CALCULATIONS
A | Technical Parameters:
Sl.No | Description | Unit | Value
1 | Working volume of the Furnace | Cum | 1758
2 | Hot metal production (Base Case: 2020-21) | tpd | 2760.06
3 | Duration of Furnace operation/ year | Days | 350
4 | Hot Blast Temp.(Base Case: 2020-21) | °C | 912
5 | Hot Blast Temp.(Proposed Case) | °C | 1200
6 | High Top Pressure (Base Case: 2020-21) | Kg/cm2g | 0.86
7 | High Top Pressure (Proposed Case) | Kg/cm2g | 1
8 | Increase in Hot Metal production on account of increase in HBT | tpd | 118.9586
9 | Increase in Hot Metal production on account of increase in HTP | tpd | 42.5049
10 | Hot Metal Production (Proposed) | tpd | 2921.5235
11 | Addl. Hot Metal prodn | Tonne | 56512.2285
12 | Eqvt. Addl. Pig Iron (93% yield) | Tonne | 52556.3725
13 | Avg. Coke Rate (Base Case: 2020-21) | kg/tHM | 453
14 | Redn. in coke rate on account of increase in HBT | kg/tHM | 18.6183
15 | Redn. in coke rate on account of increase in HTP | kg/tHM | 3.171
16 | Avg. Coke Rate (Proposed Case) | kg/tHM | 431.2107
17 | Redn. in Coke Rate | kg/tHM | 21.7893
B | Benefits :
Sl.No | Description | Unit | Quantity (t) | Rate (Rs/t) | Amount (Rs. Cr)
1 | Contribution from Addl. Pig Iron (Avg NSR 2018-21 & VC-H1, 2021-22) | Tonne | 52556.3725 | 5487.3333 | 28.8394
2 | Savings in coke consumption (VC- H1, 2021-22) | Tonne | 22280.2833 | 23586.55 | 52.5515
| Sub-total (B) |  |  |  | 81.3909 |  |  | CO gas | 1NM3 | 4200 | kCal | 1GCal= | 4.18*10^6 | KJ
C | Expenditure: | [6 empty] | BF Gas | 1NM3 | 780 | kCal
1 | Addl. Steam (6 tph) | Tonne | 50400 | 1176.36 | 5.9289
2 | Addl. BF Gas (20000 Nm3/h) | Gcal | 131040 | 1080.19 | 14.1548
2 | DM water make up for stove @ 73 M3/hr | ThM3 | 0 | 1935.5 | 0
3 | Power @ 50kWh | MW | 0 | 5072.7 | 0
4 | Secondary Industrial Water Make up @ 5M3/hr | ThM3 | 0 | 786.44 | 0
5 | Nitrogen @ 25 NM3/hr | ThNM3 | 0 | 2216.26 | 0
6 | Repair & Maint. @ 2.5% of CC net of ITC |  |  |  | #REF!
| Sub-total (C) |  |  |  | #REF!
| Gross Margin (B-C) | Rs. Cr. |  |  | #REF! | 49.8162 | 133.9472
[6 empty] | 108.3937 | 71.4197
Basis for benefits considered due to HBT rise:
|  |  | Base case | Proposed | Incr/ Decr
| Production | tpd | 2760.06 | 2921.5235 | 161 |  | 2879.0186
| Coke Rate | kg/tHM | 453 | 431.2107 | -22
| HBT | Deg C | 912 | 1200 | 288
| Hot Blast Temp. Increase | incr. in BF productivity for every 100 deg rise in HBT | decr. in coke rate for every 100 deg rise in HBT | Temp. Increase | Coke Rate | Production
| 900-1000C | 2% | 2% | 88 | 7.9728 | 48.5771 | 158.9795 | 2% increase in production for every 100 oC HBT increase
| 1000-1100C | 1.5% | 1.5% | 100 | 6.795 | 41.4009 | 118.9586 | My calculation
| 1100-1200C | 1.05% | 0.85% | 100 | 3.8505 | 28.9806 | 43.0531 | 3.3% decrease in coke rate for every 100 oC HBT increase
| Average | 1.517% | 1.45% | Top Pressure Effect | 3.171 | 42.5049 | 18.6183 | My calculation
|  |  |  | Resultant Value | 431.2107 | 2921.5235
Effect of top pressure
1 | Top Pressure (Base Case) | Kg/cm2g | 0.86
2 | Top Pressure (Proposed case) | kg/cm2g | 1
3 | Increase in productivity due to top pressure change |  | 1.54% | 1.1% increase in production for every 0.1 kg/cm2 increase in top pressure
4 | Decrease in coke rate due to top pressure change | kg/tHM | 0.7% | 0.5% decrease in coke rate for every 0.1 kg/cm2 increase in top pressure
Loss of contribution during addl. s/d period of 120 days
1 | HM prodn.in Base Case | t | 966021
2 | Duration of BF shutdown envisaged | days | 180
3 | Sheduled Shutdown | days | 180
4 | Addl. shutdown period reqd | days | 0
5 | HM production loss during addl S/D | tonnes | 0
6 | Equivalent Pig Production | tpa | 0
7 | Contribuion loss from hot metal | Rs Cr. | 0
DATA REQUIRED FOR GROSS MARGIN CALCULATIONS (Assgn No. 02/DE/4906)
Base Data
| Item | Unit | 2018-19 | 2019-20 | 2020-21 | Avg. 3 years
| Hot Blast Temp. | oC | 901 | 869 | 912 | 894
| HM production, tpd | tpd | 2681 | 2827 | 2760.06 | 2756.02
| Coke Rate, kg/thm | Kg/tHM | 465.9955 | 492.5197 | 453 | 470.7264
| Top Pressure, kg/cm2 | kg/cm2 | 0.89 | 0.86 | 0.86 | 0.87
| Steam, tph | tph | 1.96 | 4 | 4 | 3.32
| BF gas consumption in stoves, Nm3/h | Nm3/h | 90000 | 90000 | 90000 | 90000
| CO gas consumption in stoves, Nm3/h | Nm3/h | -- | -- | -- | --
| DM water in close loop for stoves valves (3 nos.), m3/h (Hot Blast Valve) | m3/h | -- | -- | -- | -- |  | Data Received from mail dated 12.01.2022 from TFL
| NSR for PIG Iron (Rs./t) | Rs./t | 27172 | 24776 | 21829 | 24592.3333 | Received from BSL on whatsapp | NSR of Pig Iron for the period Apr'21 to Sept'21 |  |  | 36956
| VC for PIG Iron (Rs./t) |  | 19215 | 17775.04 | 15018.09 | 17336.0433 | Actual cost data from BSL | Actual variable cost of pig iron for the period of Apr'21 to Sep'21 |  |  | 19105
| Productivity | t/m3/d (WV) | 1.525 | 1.608 | 1.57 | 1.5677
Benefits to be considered on account of HBT rise:
|  |  | Base case | Proposed | Incr/ Decr
| Production | tpd | 2760.06 | 2919.0395 | 158.9795 | 2% increase in production for every 100 oC HBT increase
| Coke Rate | kg/tHM | 453 | 409.9469 | -43.0531 | 3.3% decrease in coke rate for every 100 oC HBT increase
| HBT | Deg C | 912 | 1200 | 288 | Increase in HBT due to upgradation of stoves by globally reputed design
Effect of top pressure
1 | Top Pressure (Base Case) | Kg/cm2g | 0.86
2 | Top Pressure (Proposed case) | kg/cm2g | 1
3 | Increase in productivity due to top pressure change | % | 1.54% | 1.1% increase in production for every 0.1 kg/cm2 increase in top pressure
4 | Decrease in coke rate due to top pressure change | % | 0.7% | 0.5% decrease in coke rate for every 0.1 kg/cm2 increase in top pressure
| In Proposed Case: |  |  | Existing
1 | Additional power consumption(net) : | kW | 0
2 | Additional secondary industrial water: | m3/h | 0
3 | Additional nitrogen consumption: | Nm3/h | 0
4 | Total Steam Consumption in proposed case | tph | 10 | 4 | 6
5 | Total BF gas consumption in stoves in proposed case | Nm3/h | 110000 | 90000 | 20000
6 | Total CO gas consumption in stoves in proposed case | Nm3/h | 0
7 | Total DM water in close loop for stoves valves (3 nos.) (Hot Blast Valve) | Nm3/h | 0
Sl.No | Item | Year | NSR(Rs/t)
1 | NSR of Pig iron |  | 24592.3333 | 3 years average Received from BSL on whatsapp
2 | VC of PI | Rs/t | 19105 | average actual cost data from BSL for Apr'21 to Sep'21
3 | Budgeted Contribution of PI | Rs/t | 5487.3333
4 | VC of BF Coke | Rs/t | 23586.55 | Actual cost data from BSL Sept'21
5 | BF gas | Rs/Gcal | 1080.19 | Actual cost data from BSL Sept'21
6 | CO Gas | Rs/Gcal | 1074.07 | Actual cost data from BSL Sept'21
7 | DM Water (make-up Water)(Rs. 1000 extra to be added over Industrial water) | ThM3 | --
8 | Power | MW | 5072.7 | Actual cost data from BSL Sept'21
9 | Secondary Industrial Water (Water Circ Cost) | TC | 935.5 | Actual cost data from BSL Sept'21
10 | Secondary Industrial Water (Make up) | TC | 786.44 | Actual cost data from BSL Sept'21
10 | Nitrogen | TC | 2216.26 | Actual cost data from BSL Sept'21
11 | Yield of Pig Iron from HM | % | 93% | Actual data from BSL based on 3 years average
12 | Steam | Rs/t | 1176.36 | Actual cost data from BSL Sept'21
| Duration of BF shutdown envisaged | days | 180
| Sheduled Shutdown | days | 180
| Addl. shutdown period reqd | days | 0
| Working volume of the Furnace | Cum | 1758
| Duration of Furnace operation/ year | days | 350
Note: Production loss due to shutdown will not be considered

## cash flow (hidden)
[17 empty] | S T E E L A U T H O R I T Y OF I N D I A L I M I T E D | [20 empty] | Annexure-6.6.2-1
| Phasing of expenditure-Beneficiation Plant | [15 empty] | #REF!
| Years | Plant | Internal | External | IDC | Total fund | Total fund incl. IDC | [9 empty] | #REF! |  |  | Start of prod.
|  | cost | Resources | Borrowing | @10% | incl.IDC | Equity | Loan | MM | Loan+MM | [6 empty] | Profitability Projections | [19 empty] | Rs. in crore
[17 empty] | Item/Year | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Yr 7 | Yr 8 | Yr 9 | Yr 10 | Yr 11 | Yr 12 | Yr 13 | Yr 14 | Yr 15 | Yr 16 | Yr 17 | Yr 18 | Yr 19 | Yr 20 | Yr 21 | Yr 22 | Yr 23 |  |  | Calculation of depreciation
|  | #REF! | #REF! | #REF! | [12 empty] | Capacity Utilisation | 0% | 70% | 80% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 0% |  |  | Rate of depreciation | 15%
| 1st. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | [6 empty] | Gross Margin from operation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Year of production | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| 2nd | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | [6 empty] | Interest | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | Check | Gross Block | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 3rd | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | [6 empty] | Depreciation |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | #REF! | #REF! | Depreciation | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PC | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | [6 empty] | Profit Before Tax (PBT) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | Net Block | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! |  |  |  |  | 34.94% | Corporate Income Tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Input Tax Credit (ITC) | #REF! | [13 empty] | 1 | [26 empty] | 95% 0f CC | 15% 1: #REF!; 15% 7: #REF!
[11 empty] | #REF! | [5 empty] | Profit After Tax (PAT) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Gross Margin | Rs cr | #REF! | [13 empty] | Cumulative PAT |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Capital cost | Rs cr | #REF!
| Input Tax Credit (ITC) | Rs cr | #REF!
| CC net of ITC |  | #REF! | [16 empty] | Start of prod.
Cash flow statement
[17 empty] | Cash-Inflows : | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Yr 7 | Yr 8 | Yr 9 | Yr 10 | Yr 11 | Yr 12 | Yr 13 | Yr 14 | Yr 15 | Yr 16 | Yr 17 | Yr 18 | Yr 19 | Yr 20 | Yr 21 | Yr 22 | Yr 23
[17 empty] | A. Cash from operations | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[16 empty] | #REF! | B. Equity/ Internal accruals | #REF! | #REF! | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | #REF! | Loan | #REF! | #REF! | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | #REF! | Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | Sl. No. | Outflow | Inflow | Net | Cor. Tax | Net | [8 empty] | (B) Cash out-flow :
|  |  | 1 | #REF! |  | #REF! | #REF! | #REF! | [8 empty] | Capital expenditure
|  |  | 2 | #REF! | #REF! | #REF! | #REF! | #REF! | [8 empty] | Equity/ Internal accruals | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 3 |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | Loan | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 4 |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | Interest payment
|  |  | 5 |  | #REF! | #REF! | #REF! | #REF! | [5 empty] | Term loan | 10% |  | Long term loan | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 6 |  | #REF! | #REF! | #REF! | #REF! | [5 empty] | WC loan | 10% |  | Working Capital
|  |  | 7 |  | #REF! | #REF! | #REF! | #REF! | [7 empty] | #REF! | Principal repayment | Yr 1: 0; Yr 4: #REF!; Yr 5: #REF!; Yr 6: #REF!; Yr 7: #REF!; Yr 8: #REF!; Yr 9: #REF!; Yr 10: #REF!; Yr 11: #REF!; Yr 12: #REF!; Yr 13: #REF!
|  |  | 8 |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | Corporate Income Tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0% |  |  | 9 |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 10 |  | #REF! | #REF! | #REF! | #REF!
|  |  | 11 |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | Cash surplus | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 12 |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | Cash surplus (Cummulative) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 13 |  | #REF! | #REF! | #REF! | #REF!
|  |  | 14 |  | #REF! | #REF! | #REF! | #REF!
|  |  | 15 |  | #REF! | #REF! | #REF! | #REF! |  |  |  | Sensitivity factor | [5 empty] | Yr 3: Start of prod.
|  |  | 16 |  | #REF! | #REF! | #REF! | #REF! |  |  |  | Cap . Cost | 1 |  |  |  | NPV & IRR CALCULATIONS:
|  |  | 17 |  | #REF! | #REF! | #REF! | #REF! |  |  |  | GM | 1 |  |  |  | Item | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Yr 7 | Yr 8 | Yr 9 | Yr 10 | Yr 11 | Yr 12 | Yr 13 | Yr 14 | Yr 15 | Yr 16 | Yr 17 | Yr 18 | Yr 19 | Yr 20 | Yr 21 | Yr 22 | Yr 22
|  |  | 18 |  | #REF! | #REF! | #REF! | #REF! |  |  |  | PTC |  |  |  | A | Outflow
|  |  | 19 |  | #REF! | #REF! | #REF! | #REF! |  |  |  | Cut off. | 1 |  | #REF! | 1 | Capital Cost (excl. IDC) | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
|  |  | 20 |  | #REF! | #REF! | #REF! | #REF! | [7 empty] | 2 | Corporate Income Tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 21 |  | #REF! | #REF! | #REF! | #REF! |  |  |  | FE Parity | 1.075 |  |  | B | Inflow
|  |  | 22 |  | #REF! | #REF! | #REF! | #REF! | [7 empty] | 1 | Gross margin | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 23 |  | #REF! | #REF! | #REF! | #REF! | [7 empty] | 2 | ITC | Yr 2: #REF!; Yr 3: #REF!
[6 empty] | #REF! |  | #REF! | [7 empty] | 3 | Production loss during addl. s/d period
[6 empty] | #VALUE! |  | #VALUE! | [7 empty] | C | Net flow
[16 empty] | 1 | Pre-tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[16 empty] | 2 | Post Tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[16 empty] | D | NPV (@ 10%), Rs Cr
[16 empty] | 1 | Pre-tax | Yr 1: #REF!; Yr 22: 0; Yr 22: 0
[16 empty] | 2 | Post-tax | Yr 1: #REF!; Yr 22: 0; Yr 22: 0
[16 empty] | E | IRR
[16 empty] | 1 | Pre-tax | Yr 1: #VALUE!; Yr 22: 0%; Yr 22: 0%
[16 empty] | 2 | Post-tax | Yr 1: #VALUE!; Yr 22: 0%; Yr 22: 0%
[17 empty] | PI | Yr 1: #REF!
Pay-back period:
[17 empty] | Operating year -----> | Yr1 | Yr2 | Yr3 | Yr4 | Yr5 | Yr6 | Yr7 | Yr8 | Yr7 | Yr8
[17 empty] | Capital cost net of cenvat, Rs Cr | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | Gross margin, Rs Cr | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | Interest on loan, Rs Cr | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | Corporate tax, Rs Cr | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | Profit after int. & tax, Rs Cr | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | Balance loan, Rs Cr | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[18 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | Payback period, Yrs | Yr1: #REF!
[17 empty] | DSCR, Year-wise |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Minimum DSCR
Maximum DSCR
[17 empty] | Avg. DSCR | Yr2: #REF!

## FA (hidden)
Annexure 6.6.2-1
#REF!
#REF!
#REF!
FINANCIAL ANALYSIS
Sl. No. | Description | Unit | Value
1 | Capital Cost (Net of ITC) | Rs crore | #REF!
2 | Gross Margin | Rs crore | #REF!
3 | NPV @ 10% discount rate (Post-tax) | Rs.crore | #REF!
4 | IRR (Post-Tax) | % | #VALUE!
SENSITIVITY ANALYSIS
Sl.No | Parameter | IRR | Cap Cost
(Post-tax)
1 | Base Case | #VALUE!
2 | Capital cost up by 10% | 14.44%
3 | Gross margin less by 10% | 13.99%
4 | Combined effect of above two factors | 12.88%
5 | FE Parity +7.5% | #VALUE! | 74.4119

## Gross Margin (hidden)
Annexure - 6.5.1-1
S T E E L A U T H O R I T Y OF I N D I A L I M I T E D
#REF!
#REF!
Gross Margin Calculation
#REF!
Sl. No. | Technical Parameters |  |  |  | Unit | Qty. |  |  |  | Coke price: |  | BF Coke purchased price as per steel mint | [8 empty] | Gross Margin | Rs. Cr. | #REF!
1 | BF Coke production envisaged from proposed Battery / year |  |  |  | t | 391000 |  |  |  | Basic | Freight | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | Interest | Rs. Cr. | 8.7878
2 | Cost of production of BF coke (Work cost) |  |  |  | Rs./t | 27547.7821 | As per actual cost sheet 2021-22 (9 month) of DSP |  |  | 35230.5556 | 2000 | 28750 | 27000 | 27700 | 27500 | 29875 | 41100 | 49500 | 46250 | 39400 | Corporate tax | Rs.cr. | #REF!
3 | Cost of purchased BF coke |  |  |  | Rs./t | 37230.5556 | Landed cost based on Met Coke data (Apr-Dec) 2021 based on steel mint data
A | Benefit from proposed Battery : Avoidance of cost towards purchase of equivalent BF coke from external sources (A) |  |  |  | Rs Cr | 1455.7147
B | Total expenditure towards own production cost of BF coke (B) |  |  |  | Rs. Cr. | 1077.1183 |  | #REF!
C | Gross Margin (savings with proposed battery)/ annum) (A-B) |  |  |  | Rs. Cr. | 378.5964
VC of Tar | Rs/Gcal | 648.04 | Std. cost 2011-12, DSP
VC of Tar | Rs/t | 5572.0034 | =36000kJ/kg*0.23884kcal/kg*1000/10^6*648
Credit of CO gas | Rs Cr | 55.7919 | =213814080 Nm3*4200kcal/Nm3/10^6*648
Calorific Value of CO gas |  |  |  | kcal/Nm3 | 4200
ANNUAL THROUGHPUT
COAL THROUGH PUT |  |  | 1755 | T/DAY | 640575 | t | considered 90 pushing per day for TE. Coal charge of 19.5 t per oven considered, BF coke considered as 69 %. |  | 1818
GROSS COKE |  |  | 77% |  | 493242.75 | t
BF COKE |  |  | 69% |  | 441996.75 | t
GAS |  |  | 561600 | nm^3/day | 204984000 | Nm3

## CashFlow (hidden)
Phasing of expenditure | [11 empty] | SAIL/ DSP | [10 empty] | CASH FLOW STATEMENT | [9 empty] | Annexure - 6.6.1-1
Years | Plant | Internal | External | IDC | Total fund | Total fund incl. IDC |  | ITC | total |  |  | #REF! | [20 empty] | #REF!
| cost | Resources | Borrowing | @10% | incl. IDC | Equity | Loan |  | net of ITC
- | - | - | - | - | - | - | - |  |  |  |  | Profitability Projections | [21 empty] | Rs. in crore
[12 empty] | Item/Year | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Yr 7 | Yr 8 | Yr 9 | Yr 10 | Yr 11 | Yr 12 | Yr 13 | Yr 14 | Yr 15 | Yr 16 | Yr 17 | Yr 18 | Yr 19 | Yr 20 | Yr 21 | Yr 22 | Yr 23 |  | Depreciation based on WDV method @ 15% for 95% of the net of cenvat value
1 year (10%) | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! |  |  |  |  | Capacity Utilisation |  |  | 0% | 80% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 15%
2nd (35%) | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! |  |  |  |  | Profit before Depr., Int. & Tax | 0 | 0 | 0 | 277.6374 | 340.7368 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 |  | Year of comm | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
3rd (33%) | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! |  |  |  |  | Interest | 0 | 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Cap cost | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | Chk total
4th Year (1 month) (4.5%) | #REF! |  | #REF! | #REF! | #REF! |  | #REF! |  |  |  |  | Depreciation | 0 | 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | Dep @15% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF!
Post Comm (10%) | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! |  |  |  |  | Profit Before Tax (PBT) | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 378.5964 |  | Net cost | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total | #REF! | 0 | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! |  | 25.17% | Corporate Income Tax | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 95.2852
[11 empty] | 1 | [26 empty] | #REF!
Gross Margin | Rs Cr | 378.5964 | [9 empty] | Profit After Tax (PAT) | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 283.3113
[12 empty] | Cumulative PAT | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Cash flow statement
[20 empty] | 0 | [12 empty] | 0
[12 empty] | (A) Cash-Inflow | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Yr 7 | Yr 8 | Yr 9 | Yr 10 | Yr 11 | Yr 12 | Yr 13 | Yr 14 | Yr 15 | Yr 16 | Yr 17 | Yr 18 | Yr 19 | Yr 20 | Yr 21 | Yr 22 | Yr 23
[12 empty] | A. Cash from operations | 0 | 0 | 0 | 277.6374 | 340.7368 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 7054.5137
[11 empty] | 0 | B. Equity/ Internal accruals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[11 empty] | #REF! | C. Loan | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #REF!
[11 empty] | #REF! | Total | #REF! | #REF! | #REF! | #REF! | 340.7368 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | #REF!
[12 empty] | (B) Cash out-flow | [23 empty] | 0
Capital expenditure
[11 empty] | 0 | Equity/ Internal accruals | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[9 empty] | assumption:total loan spent for capital expenditure |  | #REF! | Loan | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #REF!
[11 empty] | 10% | Interest payment (from 4th year onwards) | 0 | 0 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | #REF!
[11 empty] | #REF! | Principal repayment (from 5th year and for 10 years) | 0 | 0 | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #REF!
[12 empty] | Corporate Income Tax | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 95.2852 | #REF!
[12 empty] | Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 95.2852 | #REF!
[12 empty] | Cash surplus | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 283.3113 | #REF!
[12 empty] | Cash surplus (Cummulative) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[21 empty] | 0 | [11 empty] | 0
NPV & IRR CALCULATIONS:
[20 empty] | 0 | [12 empty] | 0
[12 empty] | Item | Yr 1 | Yr 2 | Yr 3 | Yr 4 | Yr 5 | Yr 6 | Yr 7 | Yr 8 | Yr 9 | Yr 10 | Yr 11 | Yr 12 | Yr 13 | Yr 14 | Yr 15 | Yr 16 | Yr 17 | Yr 18 | Yr 19 | Yr 20 | Yr 21 | Yr 22 | Yr 23 | NPV | IRR(Pre-tax) | IRR(Pre-tax) | PI
[11 empty] | A | Outflow
[9 empty] | #REF! | #REF! | 1 | Capital Cost (excl. IDC) | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 2 | Corporate Income Tax | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 95.2852
[12 empty] | Total outflow | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 95.2852
[11 empty] | B | Inflow
[11 empty] | 1 | Gross margin | 0 | 0 | 0 | 277.6374 | 340.7368 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964
[10 empty] | #REF! | 2 | ITC on GST + salvage Value | Yr 4: #REF!; Yr 5: #REF!; 0 Yr 23: #REF!
[12 empty] | Total inflow | 0 | 0 | 0 | #REF! | #REF! | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | 378.5964 | #REF!
[11 empty] | C | Net flow
[11 empty] | 1 | Pre-tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[11 empty] | 2 | Post Tax | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[11 empty] | D | NPV (@ 10%), Rs Cr
[11 empty] | 1 | Pre-tax | Yr 1: #REF!
[11 empty] | 2 | Post-tax | Yr 1: #REF!
[11 empty] | E | IRR
[11 empty] | 1 | Pre-tax | Yr 1: #VALUE!
[11 empty] | 2 | Post-tax | Yr 1: #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Fin. Summary (hidden)
Annexure - 6.6.2-1
S T E E L A U T H O R I T Y OF I N D I A L I M I T E D
#REF!
#REF!
FINANCIAL ANALYSIS
#REF!
1 | Capital Cost net of ITC | Rs.Cr. | #REF!
2 | Gross Margin | Rs.Cr. | 378.5964
3 | NPV @ 10% (Post tax) | Rs.Cr. | #REF!
4 | I R R (Post Tax) | % | #VALUE! |  | 6 months | 1 yr | 1.5 Yr | 2 Yrs
[5 empty] | 189.2932 | 378.5864 | 567.8797 | 757.1729
Capital cost |  |  | 1
GM |  |  | 1
Purchase price of BF coke |  |  | 1
Sensitivity Analysis |  |  |  | IRR |  |  |  | NPV
|  | IRR |  | 5% | 10% | 15% |  | 5% | 10% | 15%
| Capital cost (+) 10% |  | 34.09% | 33.52% | 32.29% | 31.15% |  | 560.6853 | 551.2666 | 541.848
| GM (-) 10% |  | 33.84% | 33.54% | 32.2% | 30.84% |  | 533.2573 | 496.4107 | 459.5641
| Combined effect of above |  | 31.53% | 32.24% | 29.8% | 27.51% |  | 523.8387 | 477.5734 | 431.2977
| Purchase price of BF coke (-) 5 % |  | 31.23% | 26.24% |  |  |  | 341.1403
| Purchase price of BF coke (-) 10 % |  | 25.3% | 15.2% |  |  |  | 97.4198

## MoM (hidden)
Record notes of meeting of the Cost Review Committee
1. Name of the Project |  | #REF!
2. Subject |  | : Revised Capital Cost Estimate & Techno-Economics
3. Assignment No. |  | : 04/DE/4747
4. Date of cost review |  | : 18.05.2022
5. Proceedings of meeting:
i. Basis for equipment only |  |  | 1EURO= | #REF! | 1 USD= | #REF! |  |  | (Forward Premium Rates)
Sl. No. | Name of the Supplier/Contractor | Scope of supply | Imported Supply |  |  |  |  | Indigenous Supply |  |  |  | Engineering estimate for additional scope of supply other than BQ/ PO |  | Total cost |  | Total cost considered (Rs in Crore): Engg. Est.
|  |  | Quoted Price |  | Normalised value (Adjusted for Cap., Escl. and excl. D&E, erection, supv. etc. if any ) | Factor for location | Price trend considered (Knocked off by) | Quoted Price | Normalised value (Adjusted for Cap., Escal. and excl. any scope like D&E, erection, Civil, Strl. etc. if any) | Factor for location | Price trend considered (BQ is already Knocked off by 10%)
|  |  | FC (in FE) | FC (Equivalent Rs. In Crore) | FC (Equivalent Rs. In Crore) |  | 0% | LC (Rs. in Crore) | LC (Rs. in Crore) | 0 | 0% | FC (Equivalent Rs. Crore) | LC (Rs. Crore) | FC (Equivt Rs. Cr) | LC (Rs. Crore)
1) Details of BQs & POs considered
a | BQ of M/s Hutni Projeckt India Ltd. dtd 15.03.2022 | Electrical exhauster of Howden make |  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF!
b | BQ of M/s Hutni Projeckt India Ltd. dtd 15.03.2023 | Spares for electrical exhauster | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF!
c | BQ of M/s Hutni Projekt Frydek Mistek (HPFM) and HPIL dtd 18.11.2021 | Naphthalene Recovery Plant | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | 10% to civil
d | BQ of M/s paul worth dated 27.01.2022 | Naphthalene Recovery Plant | 12000000 Euro | #REF! | #REF! | [9 empty] | #REF! | Not considered
e | Engineering Estimate /BQs/POs | All other items except above | [10 empty] | #REF! |  | #REF! | #REF!
| Sub total |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 0 | #REF! | #REF! | #REF!
2) Details of POs referred
a. | Contract of Acme automation at BSL-T&C(M)/A6171/PP/476 for installation of 33 Electronic WF at Sinter plant dt. 17.01.2020 | 33 electronic weigh feeder of different capacity. Individual cost of BWF of different capacity is not provided in contract. |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | Not considered
b. | PO of M/s Schenk for beltweigh scale of 1000 TPH with PO no. 313103061140/0001 dt: 19.04.2014 | Beltweigh scale of 1000 TPH | [13 empty] | Not considered
[17 empty] | #REF! | #REF!
2) Details of earlier POs considered
| NA |  |  | #REF! |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0
|  |  | (Rs. in Crore.) | [11 empty] | (Rs. in Crore)
ii) | Estimate considered for the Equipment of the Project= |  | #REF! |  | Estimate considered during previous issue of capital cost (base date 3rd Quarter 2020)= | [9 empty] | 164.1064
iii) | Reasons for selecting above cost:
a) | The committee noted that the previous Capital cost estimate for subject project was Rs. 390.46 Cr net of ITC ( base date of 3rd Quarter 2020) which was based primarily on Engineering estimates, BQs/POs. However, a large part of the engineering estimate was based on previous projects of rebuilding of COB with suitable escalations.
b) | Committee discussed on BOQ along with cost & supporting documents submitted by TFL and concerned TFM members .
c) | For supply cost of equipment, BQ, PO & engg estimates for the equipment mentioned at Sl. No. a ,b,c & e have been considered. Cost review committee noted that as per practice for coke oven battery, capital cost estimate for the subject project has been prepared primarily on the basis of engineering estimate. However, a large part of the engg est is based on recently ordered values of COB#2, RSP and capital cost estimate for COB#6 at BSL ( 02/4099, Cost Committee on 08.09.2021) with suitable escalations.
d) | Impact on total basic cost due to change in scope of subject project from previous estimate of capital cost is Rs. 60.58 Cr. Details of change in scope and its impact on basic cost is attached.
e) | Cost committee noted that after accounting for change in scope and its associated cost, basic cost escalation due to time lapse is about 43% considering the current market scenario and location fator from previous issue of capital cost (base date 3rd Quarter 2020).
f) | Refractory cost is based on various latest BQs with escalation for time lapse. Cost committee delibrated to knockdown Silica bricks & Mortar cost by 15% which is based on BQ of M/s OCL Dalmia Refractories dated 31.12.2021 as it's cost appeared on higher side.
g) | Erection cost of refractory is based on engineering estimate instead of normative provisions. Rate of Inspection of refractory is considered as Rs.10000/Manday for 1940 mandays and rate of refractory erection is considered Rs. 6500/Ton.
h) | Rs. 5.04 Cr over and above normative provisions has been considered towards equipment erection for heating up, commissioning and post commissioning charges.
i) | Oven machines (Pkg-2) cost are based on discussion of TFM (Mech.) held with M/s BEC. It concluded that rate should be about 35% raised over order price for COB#2, RSP Oven machines. As the order price of RSP is above 10% more than estimate hence, the cost committee decided to increase basic rate for subject project by 45% over rate considered for COB#2 RSP.
J) | Civil works cost has been prepared on the basis of DSR 2021. Cost committee noted that cost of civil works in previous capital cost estimation was based on DSR 2018.
k) | Electrical cost estimation is based on engg estimate based on BQs/Pos and M/s. Havells price list of DEC-2021(with 20 % discount).
l) | P.C.&A. cost estimation considered engg. Estimate , recent BQs with 10% discount and previous BQs/POs with suitable escalation on the basis of WPI (all commodities).
m) | Cost committee considered structure/pipes rate as prevailing market rate. Rate for Heat resistant casting is based on lead section discussion with M/s Mecon.
iv) | Complete scope:
Sl. No. | Description | Basic Cost |  |  | Factor for location/ Area of difficulty | Total | Remarks
|  | FC (Eq Rs. in Crore) | LC (Rs. In crore)
1 | Equipment + Tech structure | #REF! | #REF! |  |  | #REF! | brought from the above
2 | Civil |  | #REF! |  | #REF! | #REF! | DSR 2021
3 | Structural | #REF! | #REF! |  | #REF! | #REF!
4 | Refarctories | #REF! | #REF! |  | #REF! | #REF! | Based on BQs
5 | Spares | #REF! | #REF! |  | #REF! | #REF!
6 | Erection and Commissioning |  | #REF! |  | #REF! | #REF! | Normative+add. Prov. for heating etc
7 | Engineering & Construction | #REF! | #REF! |  | #REF! | #REF! | 2.5% for owner, 5.0% for contractor
8 | Taxes & Duties incl. Frt | #REF! | #REF! |  | #REF! | #REF!
9 | Foreign Supervision | #REF! |  |  | #REF! | #REF!
10 | Foreign Training | #REF! | 0 |  | #REF! | #REF!
10 | CER & Env. Clearance |  | #REF! |  |  | #REF!
11 | Contingency | #REF! | #REF! |  | #REF! | #REF! | @5%
12 | Other (IDC) |  | #REF! |  |  | #REF!
14 | ITC |  | #REF! |  |  | #REF!
| Total | #REF! | #REF! |  |  | #REF!
v. TFL confirmed that the BOQ considered for preparing capital cost is for the total scope of work for the subject project.
vi. Implementation schedule : 37 months (from stage-II approval). Cost committee noted that implementation schedule was 30 months from stage-II during previous capital cost estimation
vii. Capital cost estimate: |  |  |  |  | (Rs. in Crore.) | [9 empty] | (Rs. in Crore)
Based on the above considerations, capital cost estimate net of ITC for the subject project = |  |  |  |  | #REF! |  |  | Capital cost estimate net of ITC for the subject project during previous issue of capital cost (base date 3rd Quarter 2020) = | [6 empty] | 390.4616
The committee deliberated on the above issues and found the same in order.
6. Following officials were present:
Sl. No. | Name | Designation | Signature
i | Mr. S Joardar | CGM & I/ c (Projects and C& S) -Chairman
ii | Mr. M. Choudhary | CGM (I&S, Steel, Rolling Mills and C.C &C)
iii | Mr. Ajay Kumar | CGM (Mechanical and U&S)
iv | Mr. Shalabh Sharma | CGM (Projects-PFC, BE, CTE, C&C & IPSS)
v | Mr. Sanjay Kumar | CGM (PC&A, Elec., C& IT)
vi | Mr. Manoj Mishra | GM & I/c (CTE)-Convenor
vii | Mr. S. Bhattacharjee | GM & I/c (C.C.&C.)
viii | Ms. Jyoti Dayal | GM (C.C.&C.)
ix | Mr. Anup Kumar | AGM (Proj-CTE)
x | Mr. R. Kashyap | Sr. Mgr. (Proj-CTE)
Also committee decided to discount recent BQs by 5%. In addition to above, committee decided to load 10% of Equipment cost on equipment for Risks, Financial Charges, and Overheads of contractor.

## Pkg Cost (hidden)
CONFIDENTIAL
Ref. No.: CET-17(4)/4004/ 31
Date: 04.02.2015
STEEL AUTHORITY OF INDIA LIMITED
#REF!
#REF! | Augmentation of facilities to supply rails for Iran export order
PACKAGE COST ESTIMATE
TS NO.: CET/01/BH/4004/TS/ME/01/R=1
| 1 EURO=Rs. | 75 |  | Rs. Crore
| 1 USD=Rs. | 68
Sl.No. | Description of Item | FC | LC | Total
1 | Design & Engineering incl. drgs. & doc. | #REF! | #REF! | #REF!
2 | Supply of Plant & Equipment Incl. Technological Structures | #REF! | #REF! | #REF!
3 | Supply of Building steel structures including sheeting and glazing |  | #REF! | #REF!
4 | Supply of Refractories | #REF! | 0 | #REF!
5 | Civil Engineering Work including all related supplies- for equipment foundation |  | #REF! | #REF!
6 | Civil Engineering Work including all related supplies- Others including dismantling |  | #REF! | #REF!
7 | Storage, handling, Erection of Plant & eqpt, Bldg. steel structure & Refractories incl. Comm. & PG tests of the facilities |  | #REF! | #REF!
8 | Foreign supervision charges in India during erection, startup, commissioning & PG test for _____mandays | #REF! |  | #REF!
9 | Foreign Training charges for _____mandays | #REF! |  | #REF!
10 | Ocean Freight, Custom, port clearance & inland transport for imported items | #REF! | #REF! | #REF!
11 | Comprehensive Marine / transit & Storage-cum-erection insurance | Included above
12 | Sub-total (1 to 11) | #REF! | #REF! | #REF!
13 | Purchaser's Scope: | 0 | [7 empty] | 0
i | BCD @7.5% on CIF |  | #REF! | #REF!
ii | Social welfare surcharge @ 10% on BCD |  | #REF! | #REF!
iii | GST @ 18 % on imported supply |  | #REF! | #REF!
iv | Income Tax @ 10 % grossed-up on imported services |  | #REF! | #REF!
v | GST @ 18 % on imported Services & IT |  | #REF! | #REF!
| Sub-total (13) | 0 | #REF! | #REF!
14 | Total Package Cost | #REF! | #REF! | #REF!
15 | Input tax credit (ITC) on GST |  | #REF! | #REF!
16 | Package cost net of ITC on GST | #REF! | #REF! | #REF!
(P. K. Mishra)
AGM (Projects-CTEB)
SAIL/CET
| 1 EURO=Rs. | 75 | 13.05.2016
| 1 USD=Rs. | 68 | -do
| Erection for imported supply | 6%
| Erection for plant & equipt | 12%
| Erection for structure | 20% | [5 empty] | Rs. Cr.
| Erection for refractory | 12%
| CD | 7.5%
Sl.No | Item | Basic cost |  | Indigenous supplies & services
|  | Imp. Items | Indg. Items | GST Ind. supply | GST Ind. services | Inland Frt & Ins | Purchaser's scope | Total
| #REF! | #REF! | #REF! | 18% | 18% | 18%
1 | Design & Engineering | #REF! | #REF! |  | #REF! |  |  | #REF!
2 | Supply of Plant & eqpt | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
3 | Supply of SW | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
4 | Supply of Tech Strs | #REF! |  | 0 |  | 0 |  | #REF!
5 | Building structures |  | #REF! | #REF! |  | #REF! |  | #REF!
6 | Refractories | #REF! |  | 0 |  | 0 |  | #REF!
7 | Civil work incl. all related supplies -Others |  | #REF! |  | #REF! |  |  | #REF!
| Civil work incl. all related supplies - Equipment foundation |  | #REF! |  | #REF! |  |  | #REF!
| Dismantling |  | #REF! |  | #REF! |  |  | #REF!
8 | Erection of Plant & eqpt |  | #REF! |  | #REF! |  |  | #REF!
| Erection of Tech Strs, |  | #REF! |  | #REF! |  |  | #REF!
| Erection of build. strs |  | #REF! |  | #REF! |  |  | #REF!
| Erection of Refractories |  | #REF! |  | #REF! |  |  | #REF!
9 | Foreign Supervision | #REF! | [5 empty] | #REF!
10 | Training | #REF! | [5 empty] | #REF!
11 | a) Ocean Freight | #REF! |  |  |  | #REF! |  | #REF!
| b) Custom, port clearance & inland trasport | [5 empty] | #REF! | #REF!
12 | Purchaser's scope | [5 empty] | #REF! | #REF!
| Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 250.1109
| ITC |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | 19.5742
[8 empty] | #REF! | 230.5368
0
0

## PBE Negotiated
CONFIDENTIAL
ANNEXURE-1
Ref. No.: CET-17(4)/5043/174
Date: 28.08.2024
STEEL AUTHORITY OF INDIA LIMITED
ROURKELA STEEL PLANT
Revamping of WG#1 & HG#6 Manual Roll Grinding Machine to CNC Roll Grinding Machine
Comparative statement of the quoted prices w.r.t. estimate
₹ Crore
Sl.No. | Description of Item | Estimate | M/s MAXIS MOTION CONTROLS PVT. LTD.- Pune
|  |  | Original Price (26.07.2024) | Negotiated Price (26.08.2024)
1 | Design & Engineering | 1.8531 | 1.2784 | 1.1684
2 | Supply of Plant & Equipment Incl. Technological Structures | 22.2107 | 25.5689 | 23.349
3 | Supply of Building steel structures including Sheeting and Glazing | 0
4 | Supply of Refractories | 0
5 | Civil Engineering Work including all related supplies- for equipment foundation | 0.095344 | 0.31961 | 0.15664
6 | Civil Engineering Work including all related supplies- Others | 0.083426 |  | 0.118
7 | Storage, Handling, Erection of Plant & Equipments & Refractories including Commisioning and PG tests of the facilities | 2.7536 | 4.7942 | 4.3896
8 | Storage, Handling and Erection of Building Steel Structures | 0
9 | Foreign Supervision charges in India during erection, startup, commissioning and PG test for _____mandays | 0
10 | Training charges: (a) For ___________ Foreign mandays, (b) For ___________Indian mandays | 0
11 | Customs, Port clearance (excluding duties & cess to be paid by Employer) and Inland transportation (for all items quoted in foreign currency) | 0
12 | Comprehensive / Transit Storage-cum-erection insurance | Included above |  | 0.064381
13 | Supply of 2 years O & M spares | 0
14 | Total Package Cost | 26.996 | 31.9611 | 29.246
15 | Input tax credit (ITC) for GST | 4.1053 | 4.8754 | 4.446
16 | Package cost net of ITC for GST | 22.8907 | 27.0857 | 24.8
17 | Variance w.r.t estimate |  | 18.33% | 8.341%
| Ranking |  |  | L-1
Note:- This is a computer generated document. This does not require signature.

## CTE Rate (hidden)
Dismantling
Equipment | 10000
Structure | 8000
refrractory | 4000
Refractory
Inspection (1940 mandays) , | 10000
Erection/Ton | 6500
Equipment erection
Heating up & commisioning (3600 mandays) | 4000
Post Commisioning(3600 mandays) | 10000
Building Structure
Structure | 110000
Rail | 120000
Technological Structure Structure
Tech. Structure | 150000
HR casting | 200000
Utility
MS Pipe (gas) | 120000
MS Pipe (water) | 110000
CI Pipe | 100000
Steam Pipe | 300000
MS compensator, water seal | 120000
Structure, support | 100000
Fabricated MS Item | 120000
SS Item | 400000

## Scope change from R1 (hidden)
Annexure to MOM dated 18.05.2021
Scope Change from R0 to R1
| Item | Unit | Quantity | Rate | Amount (Rs. in Lakh)
1 | Hydrojet Cleaner | Nos | 1 | #REF! | #REF!
2 | Battery operated vehicle | Nos | 1 | #REF! | #REF!
3 | Pusher side & Coke side service platform of Refractory Paving in place of Cast Iron Paving |  | 1 | -696000 | -6.96
4 | #REF! | M | #REF! | #REF! | #REF!
5 | Bench Vice | Nos | 1 | #REF! | #REF!
6 | Roughing and grinding machine | Nos | 1 | #REF! | #REF!
7 | Drilling Machine | Nos | 1 | #REF! | #REF!
8 | Underslung crane inplace of manual winch | Nos | 1 | #REF! | #REF!
9 | #REF! | Nos | 1 | 83820302.1516 | 838.203
10 | Conveyor galleries dismantling | MT | 550 | #REF! | #REF!
11 | Coveyor galleries new fabrication | MT | 550 | #REF! | #REF!
12 | Upgradation of rail | MT | 90 | #REF! | #REF!
13 | #REF! | Nos | 2 | #REF! | #REF!
14 | #REF! | MT | #REF! | #REF! | #REF!
15 | Electrical Addition |  |  |  | #REF!
16 | Electrical Deletion |  |  |  | -132
17 | #REF! | Nos. | 1 | #REF! | #REF!
18 | #REF! | Nos. | 1 | #REF! | #REF!
19 | #REF! | Nos | 1 | #REF! | #REF!
| Sub Total (Equ.+ Structure + Refractory) |  |  |  | #REF!
20 | Civil |  |  |  | 1730.0705
Total (Rs. In Cr) |  |  |  |  | #REF!
| NRU basis changed to BQ from Engg estimate resulting in differnce |  |  |  | 3369

## Civil scope change from R1 (hidden)
Civil works |  |  | Qty | Rate | Amt (Rs. in Lakh)
1 | Excavation | Cum | 13331 | 473.3043 | 63.0962
2 | PCC M10 | Cum | 349 | 7253.1739 | 25.3136
3 | RCC-M25 | Cum | 5619 | 11410.3478 | 641.1474
4 | Non-Shrink Grout | Cum | 5 | 50000 | 2.5
5 | HRC M30 | Cum | 60 | 13623.0217 | 8.1738
6 | Reinforcement | MT | 767 | 77956.5217 | 597.9265
8 | Inserts | MT | 8 | 100000 | 8
10 | IPS Flooring | Sqm | 720 | 473.913 | 3.4122
14 | Brickwork -full brick | Cum | 569 | 7317.087 | 41.6342
15 | 20mm thk plaster | Sqm | 1824 | 349.6957 | 6.3784
16 | 15mm thk plaster | Sqm | 1604 | 295.3913 | 4.7381
17 | 6mm thk plaster | Sqm | 2772 | 253.05 | 7.0145
18 | Weatherproof paint | Sqm | 1824 | 213.0435 | 3.8859
19 | Whitewashing | Sqm | 4320 | 28.2174 | 1.219
20 | Boulder Soling | Cum | 180 | 1562.8696 | 2.8132
21 | APP | Sqm | 696 | 490 | 3.4104
22 | Steel Doors | Sqm | 19 | 7234.8261 | 1.3746
23 | Windows | Sqm | 31 | 7234.8261 | 2.2428
25 | False floor | Sqm | 24 | 4701.8696 | 1.1284
27 | RCC/PCC Dismantling | Rm | 2176 | 2546.1739 | 55.4047
32 | Piling (600 dia) | Rm | 4056 | 3413.535 | 138.453
33 | DPC | Sqm | 32 | 322.4783 | 0.10319
34 | Plinth Protection | Sqm | 70 | 592.7391 | 0.41492
35 | False Ceiling | Sqm | 684 | 1582.6522 | 10.8253
52 | Diamond Wire Saw cutting | Sqm | 20 | 6000 | 1.2
53 | Vibration Isolation System (Spring) | Rupees | 1 | 800000 | 8
54 | PVC tiles | Sqm | 684 | 1500 | 10.26
55 | SS inserts | MT | 13 | 400000 | 52
29 | Rail tracks Laying | Rm | 80 | 30000 | 24
30 | Rail tracks Dismantling | Rm | 80 | 5000 | 4
|  |  |  | Total | 1730.0705

## Pkgcost (hidden)
CONFIDENTIAL
Ref. No.: CET-17(4)/3579/180
Date: 05.11.2022
STEEL AUTHORITY OF INDIA LIMITED
BOKARO STEEL PLANT
Replacement of Turbine and Auxiliaries for Turbo Blower # 5 at TBS
PACKAGE COST ESTIMATE
TS No.: CET/02/RN/3579/TS/UT/01/R=3, October 2021
₹ Crore
Sl.No. | Description of Item | FC | LC | Total |  |  | Total
1 | Design & Engineering | 0 | 3.621 | 3.621 |  |  | 3.621
2 | Supply of Plant & Equipment Incl. Technological Structures | 0 | 61.6262 | 61.6262 |  |  | 61.6262
3 | Supply of Building steel structures including sheeting and glazing |  | 0.45274 | 0.45274 |  |  | 0.45274
4 | Supply of Refractories | 0 | 0 | 0 |  |  | 0
5 | Civil Engineering Work including all related supplies- for equipment foundation |  | 1.1891 | 1.1891 |  |  | 1.1891
6 | Civil Engineering Work including all related supplies- Others |  | 2.8667 | 2.8667 |  |  | 2.8667
7 | Storage, Handling, Erection (including dismantling ) of Plant & Equipments & Refractories including Commisioning and PG tests of the facilities |  | 7.4488 | 7.4488 |  |  | 7.4488
8 | Storage, Handling and Erection of Building Steel Structures |  | 0.083072 | 0.083072 |  |  | 0.083072
9 | Foreign Supervision charges in India during erection, startup, commissioning and PG test for ____mandays | 0 |  | 0 |  |  | 0
10 | Training charges: (a) For ___________ Foreign mandays, (b) For ___________Indian mandays | 0 |  | 0 |  |  | 0
11 | Customs, Port clearance (excluding duties & cess to be paid by Employer) and Inland transportation (for all items quoted in foreign currency) | 0 | 0 | 0 |  |  | 0
12 | Comprehensive Marine / transit & Storage-cum-erection insurance |  | Included above | Included above
13 | Supply of 2 years O & M spares | 0 | 0 | 0 |  |  | 0
14 | Sub-total (1 to 11) | 0 | 77.2877 | 77.2877 |  |  | 77.2877
15 | Purchaser's Scope: | 0 | [8 empty] | 0
i | BCD @5% on CIF |  | 0 | 0 |  |  | 0
ii | Social welfare surcharge @ 10% on BCD |  | 0 | 0 |  |  | 0
iii | GST @ 18 % on imported supply |  | 0 | 0 |  |  | 0
iv | Income Tax @ 10 % grossed-up on imported services |  | 0 | 0 |  |  | 0
v | GST @ 18 % on imported Services & IT |  | 0 | 0 |  |  | 0
| Sub-total (15) | 0 | 0 | 0 |  |  | 0
14 | Total Package Cost | 0 | 77.2877 | 77.2877 |  |  | 77.2877
15 | Input tax credit (ITC) for GST |  | 11.2763 | 11.2763 |  |  | 11.2763
16 | Package cost net of ITC for GST | 0 | 66.0114 | 66.0114 |  |  | 66.0114
This is a computer generated document. This does not require signature.
| 1 EURO=Rs. | 75 | 13.05.2016
| 1 USD=Rs. | 68 | -do
| Erection for imported supply | 6%
| Erection for plant & equipt and refractory (imported too) | 12%
| Erection for structure | 20%
| Erection for refractory | 12%
| CD | 7.5% | [5 empty] | Rs. Cr.
Sl.No | Item | Basic cost |  | Indigenous supplies & services
|  | Imp. Items | Indg. Items | GST Ind. supply | GST Ind. services | Inland Frt & Ins | Purchaser's scope | Total
| 5% |  | 5% | 18% | 18% | 0%
1 | Design & Engineering | 0 | 3.0687 |  | 0.55236 |  |  | 3.621
2 | Supply of Plant & eqpt |  | 51.2016 | 9.2163 | 0.18433 | 1.024 |  | 61.6262 | 1.024
3 | Supply of SW |  |  | 0 | 0 | 0 |  | 0
4 | Supply of Tech Strs |  |  | 0 | 0 | 0 |  | 0
5 | Building structures |  | 0.352 | 0.06336 | 0.0057024 | 0.03168 |  | 0.45274
6 | Refractories |  |  | 0 | 0 | 0 |  | 0
7 | Civil work incl. all related supplies -Others |  | 2.4294 |  | 0.43729 |  |  | 2.8667
| Civil work incl. all related supplies - Equipment foundation |  | 1.0077 |  | 0.18139 |  |  | 1.1891
8 | Erection of Plant & eqpt |  | 6.3125 |  | 1.1363 |  |  | 7.4488
| Erection of Tech Strs, |  | 0 |  | 0 |  |  | 0
| Erection of Refractories (Check!) |  | 0 |  | 0 |  |  | 0
| Dismantling |  |  |  | 0 |  |  | 0
| Erection of build. strs |  | 0.0704 |  | 0.012672 |  |  | 0.083072
9 | Foreign Supervision | [6 empty] | 0
10 | Training | [6 empty] | 0
11 | a) Ocean Freight | 0 | [5 empty] | 0
| b) Custom, port clearance & inland trasport |  |  |  |  | 0 | 0 | 0
12 | Supply of 2 years O&M spares |  | 0 | 0 | 0 | 0 |  | 0
13 | Purchaser's scope | [5 empty] | 0 | 0
| Total | 0 | 64.4423 | 9.2796 | 2.51 | 1.0557 | 0 | 77.2877 |  | 250.1109
| ITC for GST |  |  | 9.2163 | 2.06 | 0 | 0 | 11.2763 |  | 19.5742
[8 empty] | 66.0114 |  | 230.5368
#REF!
#REF!
0
0