## Basic cost after ED review
Unnamed: 0 | Replacement of Benzol Storage unit at CO&BPP at BSL [Assign. No.02/DE/5071] | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7
A | As per Consolidated BQ from M/s BTL EPC Ltd (Bengal Tools) (Rs.Cr) - considered after 20% knockdown for Cap.Cost
| Description | Unit | Basic Cost | GST | Total |  | Chk
1 | Plant & Equipment incl. Technological Structures |  | 172695279 | 31085150 | 203780429 |  | 31085150.22
2 | Building Steel Structures including Sheeting and Glazing |  | 22055481 | 3969987 | 26025468 |  | 3969986.58
3 | Civil Work for Equipment Foundation |  | 92253260 | 16605587 | 108858847 |  | 16605586.8
4 | Civil Work others |  | 2000000 | 360000 | 2360000 |  | 360000
5 | Erection of Plant & Equipments and Tech Str. |  | 59223080 | 10660154 | 69883234 | Considered in erection | 10660154.4
6 | Erection of Building Str. |  | 5000000 | 900000 | 5900000 |  | 900000
7 | Training charges: for 30 Indian mandays |  | 760000 | 136800 | 896800 |  | 136800
8 | Design & Engineering |  | 18733676 | 3372062 | 22105738 |  | 3372061.68
9 | Comprehensive/ Transit, Storage cum erection Insurance |  | 936684 | 168603 | 1105287 |  | 168603.12
10 | Total Contract Price |  | 373657460 | 67258343 | 440915803
| ITC |  |  |  | 62028356
| Contract Price net of ITC |  |  |  | 378887447 | 378887445 (As quoted)
As per Item wise estimate
| Description | Unit | Qty | Rate (Rs.) | Amt (Rs. L) | Basis
Plant & Equipments
| Technological | [5 empty] | ARS Infra
1 | Benzol storage tank (4 nos.) | ton | 250 | 200000 | 500 | Engg Est. | 558
2 | Benzol pumps (1W+1S), 50 m3/h, head-20m, motor (5.5KW, FLP ) | Nos. | 2 | 889333.6605 | 17.7867 | P.O. No.-5000003902, dtd 06.03.2021, ISP for benzol pump for 10 m3/h, head-20 m, Price @Rs268722/- (FLP motor not included in price). FLP motor for 10 m3/h is around Rs 40000/- | 750000
3 | Flexible Loading arms (1W+1S) for tanker loading | Nos. | 2 | 100000 | 2 | Price taken from India Mart
4 | Benzol pipe (DN 80) [around 400 m @ 1200/m] | Lot |  |  | 4.8 | Engg estimate based on BQ for pipe
5 | Valves & fitting for benzol line of DN 80 (14 valves @ 50000/-) | Lot |  |  | 7 | Engg estimate based on BQ for Valves
| Sub Total |  |  |  | 531.5867
UTILITIES & SERVICES
1 | Pump;273m3/h;88 m head;Flame Proof motor: 90 kw | No. | 2 | 1232070.5923 | 24.6414 | BQ of M/s Wilo Mather Platt Ref: E-P-CET-001 dated 21.10.2021+ WPI escaln; 15% electrical cost replaced by Flame Proof Motor cost ref. taken from Internet reference for 6P Induction Motor | 128.3/120.4
2 | Diesel Pump;273m3/h;88 m head;Battery Bank and Panel | No. | 1 | 653112.9699 | 6.5311 | PO of M/s Phoenix Engg placed on M/s Wilo Mather Platt dated 21.11.2019+ WPI escaln | 128.3/112.8
3 | Diesel tank; 200 lit capacity;MS 3mm thk Fabricated; IS 2062 (In Kg) | Ton | 0.05 | 135000 | 0.0675 | Engg estimate & BQ for Valves and fittings
4 | Jockey Pump;11m3/h;88 m head;Flame Proof motor: 7.5 kw | No. | 1 | 157228.2051 | 1.5723 | BQ of M/s Wilo Mather Platt Ref: E-P-CET-001 dated 21.10.2021+ WPI escaln.; 15% electrical cost replaced by Flame Proof Motor cost ref. taken from Internet reference for 6P Induction Motor | 128.3/120.4
5 | Sump Pumps10m3/h;20 m head;Flame Proof motor: 5.5 kw | No. | 2 | 242147.1897 | 4.8429 | BQ of Wilo Mather Ref: MP/GI/JA/SW/F/22/SQ1775 dated 25.02.22+WPI escaln; 15% electrical cost replaced by Flame Proof Motor cost ref. taken from Internet reference for 6P Induction Motor | 128.3/122
6 | Foam Solution Pump;10m3/h;20 m head;Flame Proof motor: 5.5 kw | No. | 2 | 242147.1897 | 4.8429 | BQ of Wilo Mather Ref: MP/GI/JA/SW/F/22/SQ1775 dated 25.02.22+WPI escaln; 15% electrical cost replaced by Flame Proof Motor cost ref. taken from Internet reference for 6P Induction Motor | 128.3/122
7 | Foam Solution tank; 1000 lit capacity;MS 3mm thk Fabricated; IS 2062 (In Kg) | Ton | 0.15 | 135000 | 0.2025 | Engg estimate & BQ for Valves and fittings
8 | Pipe Line for Fire Fighting/ Water Cooling; IS 1239: Heavy Pipe DN 200; IS 3589 Pipe DN 150 Pipe DN 80 Pipe DN 40 Pipe DN 25 Pipe DN 15 Including Pipe Fittings, strainers, Bellows etc | Ton | 40 | 135000 | 54 | Engg estimate
9 | Valves and Fittings for Fire Hydrant Size 80 DN and Cooling System including 4 nos.Fire Hydrant post, Flexible hoses , Sprinklers, Valves & Fittings+Deluge Valves Size DN 65 + 4 nos.Water cum Foam Monitors etc | Lot | 1 | 675000 | 6.75 | BQ of M/s SWIMS TECHNOLOGIES PVT LIMITED, dtd.: 24.01.22 followed by WPI escalation; Various sizes and types of valves is attached in working Excel sheet BQ
10 | Nitrogen Piping including Buffer vessels, valves, fittings, etc. including PRS station for N2 blanketting | Lot | 1 | 2000000 | 20 | Engg estimate & BQ for Valves and fittings
11 | Steam Piping including valves and fittings, Insulation of 65mm thk, Purging points ball valves and flexible hoses of 25 DN etc. | Lot | 1 | 2100000 | 21 | Engg estimate & BQ for Valves and fittings
12 | Clean Agent; Including 4 nos. Cylinder, piping, Panels and Installation | Lot | 1 | 1500000 | 15 | Based on BQ reference from M/s Kalptaru and De's Technico ltd.
13 | Passive Fire Protection System for 260m cable trench and 8 nos. opening Sealing (lot) | Lot | 1 | 613000 | 6.13 | Engg. Estimate based on online net reference
14 | Dry pressurized ventilation system;Fan flow: 9500 Nm3/hr, RPM: 1000 with Motor of 1.5 kw for exhaust ventilation | Set | 5 | 19181.0631 | 0.95905 | BQ of M/s S.H. Engineering Pvt. Ltd. Dated oct 2021 with WPI escaln | 128.3/120.4
15 | Split Air conditioning system; Capacity: 2 TR; Water Cooled | Set | 3 | 49018.2724 | 1.4705 | BQ of M/s Voltas Ltd. Ref.: VL/UPBG/SAIL/SK/26112021/230 Dated Nov 2021 with WPI escaln
16 | Fire fighting system - portable fire extinguishers DCP | Nos. | 3 | 3000 | 0.09 | BQ of M/s SAFEX dated Jan 21. escalated 11% as per wpi (machinery & equip)
17 | Fire fighting system - portable fire extinguishers CO2 | Nos. | 5 | 7000 | 0.35
| Sub Total |  |  |  | 168.4503
| Mechanical | Unit | Qty | Rate (Rs.) | Amt (Rs. L)
1 | Manual Hoist (at Benzol pump house ) Capacity-3t Lift-5m, Travelling length-(8+2)10m | No. | 1 | 13250.3472 | 0.1325 | Refer No. : 4140078950/21C02723096 Dated : 25.03.2022 M/s KEPRO TOOLS & EQUIPMENTS PVT LTD | 128.3/122.7
2 | Geared Travelling Trolley (Manual operated) Capacity-3t | No. | 1 | 14492.5672 | 0.14493 | Refer No. : 4140078950/21C02723096 Dated : 25.03.2022 M/s KEPRO TOOLS & EQUIPMENTS PVT LTD
3 | Electric Hoist travelling type (at Fire hydrant pump house) Capacity-3t Lift-5m, travelling length-15m | No. | 1 | 398750 | 3.9875 | Refer BQ CCE-13368-1, Date - 28/02/2023 of Century Crane Engineers (P) Ltd
| Sub Total |  |  |  | 4.2649
Electricals
Equipment
1 | Electrical equipment tapping of power from existing LT switchboard, transformers, PMCC panel. illumination earthing, etc. | Lot | 1 | 17627000 | 176.27 | Engg calculation based on purchase orders/ BQs of individual equipment
Cables
1 | HT,LT XLPE insulated FRLS power & control cables Cable | Lot | 1 | 5050000 | 50.5 | Based on Havells Price List dated 30.01.23 with 25% discount & 11.5% pricing on the account of FRLS PVC outer sheathing & extruded PVC inner sheathing
| Total (Electrics) |  |  |  | 226.77
Instrumentation & Control System
1 | Instrumentation System | Lot |  |  | 112 | CDMS= 90%, Engineering Estimate=10%
2 | PLC System (200 IOs @ 10000/-) | Lot |  |  | 20 | Engineering Estimate
3 | Fire detection and alarm system | Lot. |  |  | 19 | CDMS:-BQ of M/s DE's Technico - Dated 08.06.2023
4 | CCTV System | Lot. |  |  | 17.4381 | CDMS:-BQ of M/s Trisim - Dated 19.02.2022 | MANUFACTURE OF COMPUTER, ELECTRONIC AND OPTICAL PRODUCTS
5 | Telecommunication System | Lot. |  |  | 1.024 | CDMS-BQ of SoneparIndia dated 07.06.2022 | 119.4/116.4 119.4/116.6
| Total Instrumentation & Control System |  |  |  | 169.4622
| Plant & Equipment Total |  |  |  | 1100.5341
Structures
A | Technological Structure
1 | Structural steel | T | 70 | 90000 | 63 | Engineering estimate
B | Building Str.
1 | CGS sheeting | Sq.M | 50 | 1200 | 0.6 | Engineering estimate
Total
CIVIL
|  | Unit | Qty. | Rate | Amt (Rs.) | DSR-2021 CLAUSE
A | Other than Equipment Foundation
1 | Dismantling of R.C.C. | cum. | 50 | 2546.17 | 1.2731 | 15.3 | Chkd
2 | Dismantling of P.C.C. | cum | 25 | 1745.3 | 0.43633 | 15.2.1
3 | Dismantling of Brick work | cum | 10 | 1476.91 | 0.14769 | 15.7.4
4 | Earth work excavation | cum. | 5430 | 473.3043 | 25.7004 | 2.8.1+0.8*2.25+0.2*1.1.2 (COL 8) | 473.3043
5 | R.C.C. of Grade M30 | cum | 325 | 11799.5217 | 38.3484 | 5.33.2.2+5*5.9.2 | 11799.5217
6 | R.C.C. of Grade M25 | cum. | 1900 | 11410.35 | 216.7966 | 5.33.2.1+ 5 * 5.9.5 | 11410.3478
7 | P.C.C. of Grade M10 | cum. | 400 | 7520.9565 | 30.0838 | 4.20.1.1+2*4.3.1
8 | Reinforcement | t | 245 | 77956.52 | 190.9935 | 5.22A.6*1000 | 77956.5217
9 | Inserts | t | 9 | 78200 | 7.038 | 10.2*1000
10 | Chequered Plate | t | 3 | 88913.0435 | 2.6674 | 10.25.1*1000
11 | Brick work (230 mm thick in 1:6 cement mortar) | cum. | 695 | 7317.087 | 50.8538 | 6.32.1
12 | Half Brick Work (115 mm thick in 1:4 cement mortar) | sqm | 500 | 885.2609 | 4.4263 | 6.13.2
13 | Plastering | sqm. | 5485 | 349.6957 | 19.1808 | 13.3.1
14 | Weather proof paint | sqm. | 3990 | 145.09 | 5.7891 | 13.46.1
15 | Acrylic emulsion paint | sqm. | 1275 | 119.8696 | 1.5283 | 13.6
16 | Boulder soling | cum | 660 | 2165.48 | 14.2922 | 16.3.2+16.4
17 | False floor with wooden particle board | sqm. | 50 | 4701.8696 | 2.3509 | 11.54.2
18 | False ceiling | sqm. | 50 | 1472.7391 | 0.73637 | 26.22.1
19 | APP | Sqm | 315 | 534.78 | 1.6846 | 14.86
20 | IPS flooring | sqm. | 300 | 473.913 | 1.4217 | 11.3.1
21 | Steel Doors & windows | sqm. | 95 | 4157.52 | 3.9496 | 10.5.1
22 | Grouting (non-shrink) | cum | 1 | 12135.4348 | 0.12135 | 5.33.1.2+8 times 5.9.2
23 | Bituminous road | sqm | 2400 | 3500 | 84
| Total cost of Civil Works for other than Equipment Foundation |  |  |  | 761.1451 |  | 143.4/132.6
B | For Equipment Foundation
| Earth work excavation | cum. | 2000 | 469.26 | 9.3852 | 2.8.1+0.8*2.25+0.2*1.1.2 (COL 8)
| R.C.C. of Grade M25 | cum. | 876 | 11410.35 | 99.9547 | 5.33.2.1+ 5 * 5.9.5 | chkd
| P.C.C. of Grade M10 | cum. | 210 | 7520.9565 | 15.794 | 4.20.1.1+2*4.3.1 | 7520.9565
| Reinforcement | t | 96 | 77956.52 | 74.8383 | 5.22A.6*1000 | chkd
| Inserts | t | 4 | 78200 | 3.128 | 10.2*1000
| Grouting (non-shrink) | cum | 2 | 12135.4348 | 0.24271 | 5.33.1.2+8 times 5.9.2
| Total cost for Equipment Foundation |  |  |  | 219.9047
| Total (Civil) |  |  |  | 981.0498
Amount (in lakh)

## PBE (R3)
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6
CONFIDENTIAL
Ref. No.: CET-17(4)/5071/2025-13
Date: 3.02.2025
STEEL AUTHORITY OF INDIA LIMITED
BOKARO STEEL PLANT
Replacement of Benzol Storage unit at CO&BPP at BSL
PRICE BID EVALUATION
Comparative statement of the quoted prices by L1 party w.r.t. estimate
Rs. Crore
Sl.No. | Description of Item | Estimate | M/s GORANTLA GEOSYNTHETICS PVT LTD
|  |  | Initial Bid dtd 23.02.24 | Bid Post negotiations dtd 18.06.24 | Revised Bid dtd 02.07.24 | Revised Bid dtd 30.01.25
1 | Design & Engineering | 1.548 | 2.891 | 2.891 | 2.891 | 2.891
2 | Supply of Plant & Equipment Incl. Technological Structures | 17.0594 | 13.865 | 16.1188 | 16.4138 | 13.865
3 | Supply of Building steel structures including sheeting and glazing | 0.0083603 | 1.77 | 0.0177 | 0.0177 | 1.77
4 | Supply of Refractories | 0
5 | Civil Engineering Work including all related supplies- for equipment foundation | 2.3659 | 5.605 | 5.31 | 5.31 | 4.8961
6 | Civil Engineering Work including all related supplies- Others | 9.8506 | 3.658 | 3.6438 | 3.4668 | 3.6581
7 | Storage, Handling, Erection (including dismantling ) of Plant & Equipments & Refractories including Commisioning and PG tests of the facilities | 2.0722 | 3.422 | 5.0144 | 5.0144 | 3.422
8 | Storage, Handling and Erection of Building Steel Structures | 0.001534 | 1.6874 | 0.02065 | 0.02065 | 1.6874
9 | Foreign Supervision charges in India during erection, startup, commissioning and PG test for ____mandays | 0
10 | Training charges: (a) For ___________ Foreign mandays, (b) For ___________Indian mandays | 0 | 0.3599 | 0.3599 | 0.0649 | 0.3599
11 | Customs, Port clearance (excluding duties & cess to be paid by Employer) and Inland transportation (for all items quoted in foreign currency) | 0
12 | Comprehensive Marine / transit & Storage-cum-erection insurance | Included above | 0.1711 | 0.1711 | 0.1711 | 0.1711
13 | Supply of 2 years O & M spares | 0 | 0.118
14 | Total Quoted Price | 32.906 | 33.5474 | 33.5474 | 33.3704 | 32.7206
15 | Input tax credit (ITC) on GST | 3.5154 | 4.032 | 4.5557 | 4.5557 | 3.9059
16 | Total Quoted Price net of ITC for GST (14-15) | 29.3905 | 29.5154 | 28.9917 | 28.8147 | 28.8147
17 | Variation w.r.t. Estimate (in %) |  | 0.004248 | -0.013571 | -0.019593 | -0.019592
This is a computer generated statement and doesn't require signature